## Summary
CONSTRUCTION OF BARAKA-CHAKA WATER EXTENSION PROJECT IN NYERI COUNTY
ITEM | ITEM DESCRIPTION | AMOUNT (KES)
1 | BILL NO. 1: Preliminaries and General | 0
2 | BILL No. 2: Baraka-Chaka Rising main | 0
3 | BILL No. 3: Baraka-Chaka/Tagwa Gravity Main
3 | BILL No. 3: Pump, Motor & Electrial Works | 0
4 | BILL No. 4: Construction of 500 M3 Ground Level High Tensile Steel Water Tank | 0
| Sub-Total (VAT Exclusive) | 0
| Add 5% Contingencies | 0
| Total | 0
| Add 16% VAT | 0
| GRAND TOTAL TO FORM OF TENDER | 0

## BIll 1_PNG
CONSTRUCTION OF BARAKA-CHAKA WATER EXTENSION PROJECT IN NYERI COUNTY
BILL NO:1 | PRELIMINARIES AND GENERAL ITEMS
ITEM NO. | ITEM DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
CLASS A: GENERAL ITEMS
Method-related charges
1.1 | Provide Kshs 500,000 as the Perfomance Bond | Sum
1.2 | Provide Kshs 500,000 for Contractor All Risk Insurance | Sum
1.3 | Provide Kshs. 100,000 for site setup establishment and removal on completion. Mobilization and demobilization of equipment and personel and disposal of all waste material away from site as directed by the project Engineer. | Ls | 1
1.4 | Provisional Sum of Ksh. 50,000 for establishment of Level Survey Datum, Setting Out of the Works | PC Item
1.5 | Provide Kshs. 600,000 for attendance to works by the supervision team | PC Item
1.6 | PC sum of 500,000 any payment for services by KURA, KENHA, KENYA RAILWAYS, NEMA, KPLC, KCG, Telecom Kenya, Water, Sewer connections etc and others of different natures that have any statutory jurisdiction over the works or own any overhead or buried service infrastructures such as cables and/ or conduits or have airspace rights or restrictions. Include any monies that may be required for their attention. | PC Item
1.7 | Percentage adjustment to PC sum for profits and overheads | %
1.8 | Provide 50,000 for any costs associated with compliance with Environmental, Health and Safety Requirements | Sum
BILL 1 TOTAL CARRIED TO SECTION COLLECTION SHEET |  |  |  |  | 0

## Bill 2_BARAKA-CHAKA RM
CONSTRUCTION OF BARAKA-CHAKA WATER EXTENSION PROJECT IN NYERI COUNTY
BARAKA CHAKA RISING MAIN
Item | Description | Unit | Qty | Rate | Amount
CLASS A : GENERAL ITEMS
A2 | Specified Requirements
A212.1 | Provide and maintain sign board per TWWDA standard sign board as directed by the Engineer and inclusive of removal after completion-location and design to be as directed by the Engineer. | nr | 1
.
Testing of the Works
Field Pressure Testing, Cleansing and Sterilisation of Pipelines
in Accordance with specifications
A260.1 | Pressure Testing Epoxy coated and Cement lined spiral weld Double Flanged Pipes , exc. 25 bars including all necessary equipment, materials and works necessary for testing, including transportation and use of water, pipe fittings, disposal of used water. | m | 100
A260.2 | Pressure Testing HDPE, exc. 8 bar including all necessary equipment, materials and works necessary for testing, including transportation and use of water, pipe fittings, disposal of used water. | m | 6878
CLASS D : DEMOLITION AND SITE CLEARANCE
D610.1 | Clearance of Pipeline wayleave of shrubs, bushes and locally dispose nominal bore 90-300mm | m | 1719.5
CLASS I : PIPEWORK - PIPES.
I412 | Epoxy coated and Cement lined spiral weld Double Flanged Steel Pipes
The rate quoted Is for supply, transport to site, setting out, pegging, laying and joint Epoxy coated and Cement lined spiral weld Double Flange pipes. The rate is deemed to include installation as directed by engineer. Including excavation depth not exceeding 2.5 m, preparation of trench surfaces; upholding sides of the excavation, disposal of excess excavated material, removal of dead services backfilling of trenches except to the extent that such work is included in classes J, K and L and backfilling of trenches. .
I412.1 | OD 160mm PN 40 | m | 100 |  |  | 700 | 11200
The rate quoted Is for supply, transport to site, setting out and pegging, laying and jointing of high density polyethylene (HDPE) PN16 pipes to KS-06-149 Part Z: 2000 including excavation and backfilling of trenches, depth not exceeding 2 m. Include for preparation of trench surfaces; upholding sides of the excavation, disposal of excess excavated material, removal of dead services except to the extent that such work is included in classes J, K and L. All pipes of OD90 mm and above shall be jointed by Butt Fusion method. All pipes of OD63mm and below shall be jointed with HDPE couplings with pressure rating equal to or greater than that specified for the pipes.
HDPE Pipeline
I712.1 | OD 160mm HDPE PN25 | m | 1000 |  |  | 1880
I712.2 | OD 160mm HDPE PN20 | m | 2000 |  |  | 2920
I712.3 | OD 160mm HDPE PN 16 | m | 3878 |  |  | 1500
Road Crossings
I422 | Provision for road Crossing sleeve Duct 250 mm Nominal bore GI pipes Class C (Provisional) | m | 36
CLASS J : PIPEWORK - FITTINGS AND VALVES
Provision and installation of fittings and valves including excavation and backfilling of trenches, depth not exceeding 1.5m. Include for preparation of trench surfaces; upholding sides of the excavation, disposal of excess excavated material, removal of dead services except to the extent that such work is included in classes I, K and L
Epoxy Coated Steel Flanged Reducers
J331.1 | Nominal Bore 150x50 mm, PN 25 (Provisional) | nr | 1
J331.2 | Nominal Bore 63x50 mm, PN 25 | nr | 6
HDPE Reducers
J631.1 | nominal bore 63 x50 mm (Provisional) PN 25 | nr | 1
J631.2 | nominal bore 63 x50 mm (Provisional) PN 40 | nr | 1
HDPE Flange Adaptor, PN 25
J651.1 | nominal bore 160mm (Provisional) | nr | 1
HDPE Stub ends Couplings to specifications
J641.1 | nominal bore 75 mm PN 40 (Provisional) | nr | 1
J641.2 | nominal bore 50 mm | nr | 6
J641.3 | nominal bore 160 mm | nr | 12
Straight specials Epoxy coated and Cement lined spiral weld PN 25 (Provisional)
J381.1 | Double flanged Spigot nominal bore 160, n.e. 0.6 m | nr | 2
J381.2 | Double flanged Spigot nominal bore 160, n.e. 1.2 m | nr | 2
J381.3 | Single flanged Spigot nominal bore 160, n.e. 0.6 m | nr | 1
J381.4 | Single flanged Spigot nominal bore 160, n.e. 1.2 m | nr | 1
J861 | Air Valves Anti-Surge Anti-Shock Air valves Airvalves to to specifications or Similar to be Approved by the Project Engineer
J861.1 | nominal bore 50 mm , PN 25 | nr | 6
J861.2 | nominal bore 50 mm , PN 40 | nr | 1
J811 | Sluice valves to BS 5163, flanged to specifications
J811.1 | nominal bore 160 mm, PN 40 | nr | 1
J811.2 | nominal bore 160 mm, PN 25 | nr | 1
J811.3 | nominal bore 80 mm, PN 40, for WO, | nr | 1
J811.4 | nominal bore 80 mm, PN 25, for WO, | nr | 2
J811.5 | nominal bore 50 mm PN 25 for AV | nr | 5
J811.6 | nominal bore 50 mm PN 40 for AV | nr | 1
|  | nr | 1
J611 | HDPE Bends, PN 25
J611.1 | nominal bore 160 mm PN 25 (Provisional) | nr | 1
J611.2 | nominal bore 90 mm PN 25 (Provisional) | nr | 1
J611.3 | nominal bore 75 mm PN 25 | nr | 3
Steel Bends, Double Flanged
J311.1 | Epoxy coated and Cement lined spiral weld PN 40,OD 150mm (90o ) | nr | 3
J311.2 | Epoxy coated and Cement lined spiral weld PN 40,OD 150mm (22.5o ) | nr | 1
J311.3 | Epoxy coated and Cement lined spiral weld PN 40,OD 150mm (30o ) | nr | 1
J311.4 | Epoxy coated and Cement lined spiral weld PN 40,OD 150mm (11.25o ) | nr | 1
J831 | Non return Valve to specifications (Provisional)
J831.1 | nominal bore 150, PN 40 | nr | 1
Junctions and branches - Tees in accordance with specifications
Epoxy coated
J321.1 | Nominal bore, All Flanged, PN 40, 150 x 150 x 150 (Provisioanl) | nr | 1
J321.2 | Nominal bore, All Flanged, PN 40, 150 x 150 x 80 | nr | 1
J321.3 | Nominal bore, All Flanged, PN 25, 150 x 150 x 80 | nr | 2
J321.4 | Nominal bore, All Flanged, PN 40, 150 x 150 x 63 | nr | 1
J321.5 | Nominal bore, All Flanged, PN 25, 150 x 150 x 63 | nr | 5
Steel Plain Flanges
J631.1 | OD 160 Steel plain flange, PN40 | nr | 1
J631.2 | OD 160 Steel plain flange, , PN25 | nr | 6
J631.3 | OD 75 Steel plain flange, PN25 | nr | 6
J631.4 | OD 50 Steel plain flange, , PN25 | nr | 1
Surge Vessel
J882.1 | Bladder Type Surge Vessel or similar as per specification and to be approved by the Engineer ( capable of hadling pressure head inclussive of water hammer of 400m) | sum | 1
CLASS K : PIPEWORK - MANHOLES, CHAMBERS AND
PIPEWORK ANCILLARIES
Construction of chambers as per drawings
K231 | Chambers
K231.1 | Ditto Airvalve chambers, depth n.e 2m | nr | 6
K231.2 | Ditto Washout chambers, depth n.e 2m | nr | 4
K231.3 | Ditto Control/Sluice valve chamber, depth n.e 2m | nr | 1
K231.4 | Ditto Meter Chamber, depth n.e 2m | nr | 1
K733 | Reinstatement
K733.1 | Allow for breaking up, and Permanent reinstatement of murram roads, Rates deemed inclusive of the provision of requisite diversion signage, controls and safety precaution. | m | 25
CLASS L : PIPEWORK - SUPPORTS AND PROTECTION,
ANCILLARIES TO LAYING AND EXCAVATION
Excavation of rock as defined in the specifications
L111 | Excavation in rock | m3 | 1256.04
L112 | Excavation in mass concrete (Provisional) | m3 | 2
L113 | Excavation in reinforced concrete (Provisional) | m3 | 2
Pipe bedding & Surround
L331.1 | Approved imported granular material as per standard drawings | m | 6978
Thrust blocks for bends, tees and blank ends. Dimensions of each
block as shown on Drawings
(provision of Concrete, reinforcement and Construction)
L711.1 | Concrete stools and Thrust Blocks (Volume: 0.2-0.5),Nominal bore n.e. 160mm; volume n.e 0.5m3 | nr | 15
K820 | Marker posts as per drawings
K820.1 | Marker posts for Sliuce Valves inscribed SV | nr | 1
K820.2 | Ditto but for Washouts inscribed WO | nr | 4
K820.3 | Ditto but for Air Valve inscribed AV | nr | 6
K820.4 | Ditto but for Water Main inscribed WM | nr | 35
BILL 2 TOTAL CARRIED TO SECTION COLLECTION SHEET

## Bill 3_PUMP
ITEMS | DESCRIPTION | UNITS | QTY | RATES | AMOUNT
1 | Pump, Motor & Electrial
1.1 | Supply, Delivery, install, Testing and commission 1 No. surface pumps as per specification provided. The selected pump to have a minimum efficiency of 70% at system duty point, motor efficiency class IE3. Pump capable to discharge a minimum of 50 m3/hour at 250m head. Include in rate for installation accessories including 50 mm2, 20 m long four core armoured copper cable and commissioning of all wiring, cabling, control panel weather proof housing, Pressure Control Switches for automatic tank filling and connection to Power . The pump should also be capable of maintaing efficiency over large pumping range but should not loose efficiency by more than 5% on either side of the duty point and Should be Complete with Sunction flange and reducer to connect to OD 160mm outlet and 200mm inlet Pipes. All the above to be done to the satifsfaction and to be appproved by the Project Engineer and as per below specification. | No. | 1
Pump Make KSB /Ritz or equal and approved quality Flow rate – 50m³/h Head – 250m Efficiency –70% and above Suction flange –DN100 Discharge flange – DN65 Discharge nominal pressure – PN40 NPSH – 2.5m or less Pumped medium – clean treated water Impeller type – multistage no of stages - 6 Installation mode – horizontal Lubrication type – Grease Shaft seal – gland parking Design – baseplate mounted Horizontal long coupled design with radial nozzles rolling element bearing on both ends and drive on the suction side
Motor Make – KSB/Ritz/Asea/ABB/Siemens/Crompton greaves or equal and approved quality Power – 55kw Voltage - 415v Frequency – 50Hz RPM – 2960 Efficiency class – IE3 Power cable – 50mm² 4core copper armoured cable -20mtrs Signal and thermostat Cable – 1.5 cu armoured cable -15mtrs Thermal protection – Thermostat
Control panel Star delta starter 240v, 125Amps ABB contactors - Din rail mounted 160Amps ABB MCCB - Din rail mounted MP204 200Amps ABB Mains power with an isolation switch Capacitor and special contactor for power factor correction 3 phase phase failure Overload relay 100A 3phase VAF digital meter Start/stop button Indicator lamps - power on, trip, no flow Flow switch No flow reset button Pressure switch Timers Selector switch – Auto, off, man Surge arrestor - 40kn Hour run meter Triple pole for surge arrestor Wall mounted control panel with adequate space to hold 2 other similar starters for future additional pump Miscellaneous - cable tray, cable glad, cable ties, cable lugs, cable duct
Suction and discharge plumbing works Designing, modification, fabrication and installation of the discharge and suction pipe fittings. The suction and discharge fittings are described in the BOQ.
Accessories Coupling – fenner flex tyre coupling Coupling guard Leakage drain plate Anchoring bolts Ball valve 150mm PN 16 Pressure gauge Automate the pump by use of pressure switch (reservoir tank is 7km away)
1year warranty A mandatory site visit Attach brochures for easy evaluation during implementation
Supply, Delivery, install, Testing of fittings and valves Including installation all associated accessories such as bolts, nuts, Washers & Gaskets and adequate supports
FITTINGS AND VALVES
Supply Delivery, Fabrication and installation of fittings and valves
2 | Suction (All Itemto be Rated Class C or PN16 and Epoxy Coated)
2.1 | Double Flange GI Pipe OD 200 | m | 20
2.2 | GI Flange OD 200mm | nr | 6
2.3 | Double Flanged Spigot GI Pipe 200 mm dia n.e 1.5m | nr | 2
2.4 | Blank Flange OD 200 | nr | 2
2.5 | All Flanged GI Bend OD 200mm | m | 2
2.6 | All Flanged Tee GI OD 200x200x160 mm | m | 3
2.7 | Sluice Valves DN 150mm | nr | 3
2.8 | Double Flanged Spigot GI Pipe 160 mm dia n.e 1.5m | nr | 3
2.9 | Flanged Reducer 160mm x 100mm | nr | 3
3 | Delivery (All Itemto be Rated PN40 and Expoxy Coated)
3.1 | Sluice Valves DN 150mm | nr | 3
3.2 | Non-Return Resilient Seated Valve DN 160mm | nr | 3
3.3 | All Flanged GI Bend DN 160 mm | nr | 3
3.4 | All Flanged Tee GI DN 160mmx160mmx160mm | nr | 3
3.5 | Double Flanged Spigot GI Pipe 160 mm dia n.e 1.5m | nr | 2
3.6 | Blank Flange DN 160 | nr | 1
3.7 | Pressure Gauge | nr | 1
3.8 | Double Flange GI Pipe DN 160 | m | 15
3.9 | GI Flange OD 160 | nr | 2
4 | Flanged Reducer 160mm x 65mm | nr | 3
5 | Allow Kshs. 2,500,000 P.C. Sum for electricity supply and connection to Pump House including a 315 KVA Transformer. Contractor is responsible for the application of electricity connection; follow up and for prompt supply and connection of electricity by KPLC. Electricity account to be held in the name of the Employer or the Water Service Provider as directed. | Sum | 1
5.1 | Percentage adjustment to PC sum for profits and overheads for item 5.0 | %
| BILL 3 TOTAL CARRIED TO SECTION COLLECTION SHEET |  |  |  | 0

## Bill 4_TANK
PROPOSED PREFABRICATED STEEL 500m³ GROUND TANK FOUNDATION
CONSTRUCTION OF 500 M3 GROUND LEVEL HIGH TENSILE STEEL WATER TANK AT KARICHEN
ITEM | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT | QTY_
1 | BILL 1 - PRELIMINARY AND GENERAL ITEMS
Specific Requirements
1.1 | Testing of the works after substantial completionas per Engineer's specifications | Ls
Testing of Materials
By Third Party Inspection (natural materials)
1.8 | Sand | No | 5
1.14 | Aggregate | No | 5
By Third Party Inspection (man-made other than pipes)
1.16 | Concrete cubes | No | 5
2.00: SUBSTRUCTURE
2 | ELEMENT N0. 1
SUBSTRUCTURE (ALL PROVISIONAL)
Excavation
2.1 | Excavate oversite average 150 mm deep to remove vegetable top soil and including cutting of shrubs, bushes and trees less than 0.5m diameter all to specifications and cart away to an approved Tip by Local Authority. | SM | 600 |  |  | 400
2.2 | Excavate to reduce levels commencing at stripped level not exceeding 1.5 m deep | CM | 180 |  |  | 157.6193
2.3 | Provision for Extra over excavation for excavating in rock: irrespective of class | CM | 50 |  |  | 35.1904
Disposal
2.4 | Load, spread and ram surplus excavated material on site as directed by Engineer | CM | 180 |  |  | 157.6193
Hardcore filling
2.5 | Provide hardcore of inert approved material well watered and compacted in 150mm thick layers and void pockets to be filled with quarry dust to Engineer's approval | CM | 80 |  |  | 63.0477
Concrete works
Plain concrete Class 15 in:-
2.6 | 100mm Blinding under ring beam | SM | 50 |  |  | 35.1904
2.7 | 100mm thick blinding to top of hardcore surface | SM | 130 |  |  | 126.0955
Vibrated reinforced insitu concrete (1:1½:3) class 25/20; with minimum cube crushing strength of 25N/mm² at 28 days as specified; in
2.8 | Beam | CM | 40 |  |  | 35.1904
2.9 | Floor slab; 250 mm thick | CM | 40 |  |  | 37.8286
Formwork
2.1 | Marine plywood formwork curved on site to both inner and outer edges of the beam | SM | 90 |  |  | 89.0443
Total carried to Summary
Mild steel reinforcement as described including cutting to length, bending and fixing including all necessary tying wires and spacing blocks;
Beams
2.11 | Mild steel Reiforcement for Beams D12 (rebars) | Kg | 160 |  |  | 137.6
2.12 | Mild steel Reiforcement for Beams D16 (rebars) | Kg | 380 |  |  | 326.163
2.13 | Mild steel Reiforcement for Beams D10 (stirrups) | Kg | 380 |  |  | 334.5679
Slabs
2.14 | Mild steel Reiforment for assorted bars for slab D10 | Kg | 3500 |  |  | 3319.7094
3 | BILL: 3 PREFABRICATED TANK
Walling
3.1 | Supply and Install Zincalume G300 AZ 150 Heavy duty Resin coated panels, bolted together using Gr 8.8 HDG specific bolts cast in situ with the beam | SM | 200 |  |  | 177.7555
3.2 | Install 2.4mm thick HDG High Tensile(HT) steel sheet metal wind girts punched and bent into profiles | LM | 120 |  |  | 79.8
3.3 | Supply and fix 700G portable propriety liner to AS/NZS 4020-2005 standards | SM | 360 |  |  | 344.3123
Dome Roof
3.4 | Hot Dipped Galvanized(HDG) truss set with varied spans and maximum span of tank diameter fabricated from 50x50mm SHS (min 300MPa) and equal angle steel to be specified and approved by the engineer | LM | 120 |  |  | 100
3.5 | Supply and install Zincalume Corrugated roof sheeting with 0.47mm AZ150 Coating or equally approved | SM | 160 |  |  | 144.0843
Tank Access
3.6 | Supply, fix and install interior and exterior ladder to include safety cage,platform, access hatch and handrails all made from HDG steel and approved steel fabricator | ITEM | 1 |  |  | 1
Supply & Install materials,pipes and fittings as per specifications to be approved by the Engineer for the following;
Inlet
3.7 | 160mm 45˚ flanged HDG Steel deflector bend with gaskets at flanges | No | 1 |  |  | 1
Sub-Total 1 page 04 Taken to collection page
3.8 | 160mm HDG steel Nozle component,double flanged spigot on one end and in the middle and include; set screws, nuts,plain washers and "o" rings | No | 1 |  |  | 1
3.9 | 160mm HDG steel profile flange | No | 1 |  |  | 1
3.1 | 160mm HDG steel backing flange | No | 1 |  |  | 1
3.11 | 160mm HDG steel coupling to join and align the flange adaptor to the nozzle component | No | 1 |  |  | 1
3.12 | 160mm HDG steel flange adaptor | No | 1 |  |  | 1
3.13 | Flanged Ball valve | No | 1
| Outlet |  |  |  |  | 1
3.14 | 160mm HDG steel anti-vortex plate to be approved by the Engineer | No | 2 |  |  | 2
3.15 | 160mm HDG steel Nozle component,double flanged spigot on one end and in the middle and include; set screws, nuts,plain washers and "o" rings | No | 2 |  |  | 2
3.16 | 160mm HDG steel profile flange | No | 2 |  |  | 2
3.17 | 160mm HDG steel backing flange | No | 2 |  |  | 2
3.18 | 160mm HDG steel coupling to join and align the flange adaptor to the nozzle component | No | 2 |  |  | 2
3.19 | 160mm HDG steel flange adaptor | No | 2 |  |  | 2
Overflow
3.2 | 200mm flanged HDG steel bell mouth | No | 1 |  |  | 1
3.21 | 200mm HDG steel Nozle component,double flanged spigot on one end and in the middle and include; set screws, nuts,plain washers and "o" rings | No | 1 |  |  | 1
3.22 | 200mm HDG steel profile flange | No | 1 |  |  | 1
3.23 | 200mm HDG steel backing flange | No | 1 |  |  | 1
3.24 | 200mm HDG steel coupling to join and align the flange adaptor to the nozzle component | No | 1 |  |  | 1
3.25 | 200mm HDG steel flange adaptor | No | 1 |  |  | 1
3.26 | 90˚ HDG steel double flanged bend | No | 1 |  |  | 1
3.27 | 65˚ HDG steel flanged on on one end to act as spout to downpipe | No | 1 |  |  | 1
3.28 | 200mm flanged HDG steel (MS) pipe for downpipe complete with pipe clamps as per drawings and specifications | LM | 4 |  |  | 4.5
Dump drain
3.29 | Provide for RCC chamber manhole to house sluice valve and complimentary accessories finished to approved standards by Engineer | ITEM | 2 |  |  | 2
3.3 | PN16, DN 300 Flanged Sluice valve complete with bolts and nuts | No | 1 |  |  | 1
Water level indicator
3.31 | Supply deliver to site and install mechanical water level monitoring installation complete with all complimentary accessories | ITEM | 1 |  |  | 1
Ventilator
3.32 | Supply and install 76mmx76mm SHS static steel ventilators from an approved steel fabricator in accordance with Engineers drawing and specifications | ITEM | 4 |  |  | 4
| BILL 4 TOTAL CARRIED TO SECTION COLLECTION SHEET |  |  |  | 0

## Bill 3_GRAVITY MAIN (hidden)
BARAKA-CHAKA/TAGWA PIPELINE EXTENSION PROJECT STORAGE TANK
BARAKA CHAKA GRAVITY MAIN
Item | Description | Unit | Qty | Rate | Amount
CLASS A : GENERAL ITEMS
A2 | Specified Requirements
Testing of the Works
Field Pressure Testing, Cleansing and Sterilisation of Pipelines
in Accordance with specifications
A260.1 | Pressure Testing HDPE, exc. 8 bar including all necessary equipment, materials and works necessary for testing, including transportation and use of water, pipe fittings, disposal of used water. | m | 500 | 50 | 25000
A260.2 | Sterilization and Flushing as per specifications | m | 1000 | 30 | 30000
CLASS D : DEMOLITION AND SITE CLEARANCE
D610.1 | Clearance of Pipeline wayleave of shrubs, bushes and locally dispose nominal bore 90-300mm | m | 500 | 50 | 25000
CLASS I : PIPEWORK - PIPES.
Provision for setting out and pegging, laying and jointing of high density polyethylene (HDPE) PN16 pipes to KS-06-149 Part Z: 2000 including excavation and backfilling of trenches, depth not exceeding 2.0m. Include for preparation of trench surfaces; upholding sides of the excavation, disposal of excess excavated material, removal of dead services except to the extent that such work is included in classes J, K and L. All pipes of OD90 mm and above shall be jointed by Butt Fusion method. All pipes of OD63mm and below shall be jointed with HDPE couplings with pressure rating equal to or greater than that specified for the pipes.
HDPE Pipeline
I712.1 | OD 160mm HDPE PN16 | m | 300 | 2150 | 645000
I712.2 | OD 90 mm HDPE PN16 | m | 300 | 1000 | 300000
Road Crossings
I422 | Provision for road Crossing sleeve Duct 250 mm Nominal bore GI pipes Class C | m | 18 | 10000 | 180000
CLASS J : PIPEWORK - FITTINGS AND VALVES
Provision and installation of fittings and valves including excavation and backfilling of trenches, depth not exceeding 1.5m. Include for preparation of trench surfaces; upholding sides of the excavation, disposal of excess excavated material, removal of dead services except to the extent that such work is included in classes I, K and L
HDPE Reducers, PN 16
J631.1 | nominal bore 160 x 90 mm (Provisional) | nr | 1 | 7000 | 7000
J631.2 | nominal bore 63 x50 mm (Provisional) | nr | 4 | 2000 | 8000
HDPE Flange Adaptor, PN 16
J651.1 | nominal bore 160mm (Provisional) | nr | 1 | 6000 | 6000
End Caps PN 16
J651.2 | nominal bore 110mm | nr | 2 | 2000 | 4000
Ranger Coupling Epoxy Coated to specifications
J341.1 | nominal bore 150 mm, PN 16 (Provisional) | nr | 1 | 4568 | 4568
J341.2 | nominal bore 150 mm, PN 16 (Provisional) | nr | 1 | 4568 | 4568
HDPE Stub ends Couplings to specifications
J641.1 | nominal bore 160 mm | nr | 2 | 5000 | 10000
J641.2 | nominal bore 75 mm | nr | 6 | 2500 | 15000
J641.3 | nominal bore 90mm | nr | 2 | 2700 | 5400
J641.4 | nominal bore 63mm | nr | 2 | 2600 | 5200
J641.5 | nominal bore 50mm | nr | 4 | 1500 | 6000
Straight specials (Provisional)
J381.1 | Double flanged Spigot nominal bore 160, n.e. 0.6 m | nr | 1 | 13000 | 13000
J381.2 | Double flanged Spigot nominal bore 160, n.e. 1.2 m | nr | 1 | 20000 | 20000
J381.3 | Single flanged Spigot nominal bore 160, n.e. 0.6 m | nr | 1 | 9000 | 9000
J381.4 | Single flanged Spigot nominal bore 160, n.e. 1.2 m | nr | 1 | 16000 | 16000
J861 | Air Valves Anti-Surge Anti-Shock Air valves Airvalves to to specifications or Similar to be Approved by the Project Engineer
J861.1 | nominal bore 50 mm , PN 16 | nr | 4 | 53000 | 212000
J861.2 | nominal bore 25 mm , PN 16 | nr | 1 | 30000 | 30000
J811 | Sluice valves to BS 5163, flanged to specifications
J811.1 | nominal bore 160 mm | nr | 2 | 46878 | 93756
J811.2 | nominal bore 80 mm | nr | 5 | 23700 | 118500
J811.3 | nominal bore 25 mm | nr | 1 | 20000 | 20000
J811.4 | nominal bore 50 mm | nr | 4 | 18000 | 72000
|  | nr | 1 | 22000 | 22000
J611 | HDPE Bends, PN 16
J611.1 | nominal bore 160 mm PN (Provisional) | nr | 2 | 9000 | 18000
J611.2 | nominal bore 90 mm PN (Provisional) | nr | 1 | 3200 | 3200
J611.3 | nominal bore 75 mm | nr | 1 | 2500 | 2500
Junctions and branches - Tees in accordance with specifications
HDPE
J621.1 | Nominal bore 150 x 150 x 63 | nr | 4 | 17000 | 68000
J621.2 | Nominal bore 160 x 160 x 75 | nr | 1 | 17000 | 17000
J621.3 | Nominal bore 90 x 90 x 75 | nr | 2 | 6000 | 12000
J621.4 | Nominal bore 90 x 90 x 50 | nr | 2 | 5000 | 10000
Steel Plain Flanges
J631.1 | OD 160 Steel plain flange | nr | 2 | 12000 | 24000
J631.2 | OD 90 Steel plain flange | nr | 2 | 5000 | 10000
J631.3 | OD 75 Steel plain flange | nr | 2 | 4085 | 8170
J631.4 | OD 50 Steel plain flange | nr | 4 | 2800 | 11200
CLASS K : PIPEWORK - MANHOLES, CHAMBERS AND
PIPEWORK ANCILLARIES
Construction of chambers as per drawings
K231 | Chambers
K231.1 | Ditto Airvalve chambers, depth 1.5 - 2m | nr | 4 | 25000 | 100000
K231.2 | Ditto Washout chambers, depth 1.5 - 2m | nr | 3 | 25000 | 75000
K231.3 | Ditto Control/Sluice valve chamber, depth 1.5 - 2m | nr | 4 | 25000 | 100000
K231.4 | Ditto Meter Chamber, depth 1.5 - 2m | nr | 1 | 25000 | 25000
K733 | Reinstatement
K733.1 | Allow for breaking up, and Permanent reinstatement of murram roads, Rates deemed inclusive of the provision of requisite diversion signage, controls and safety precaution. | m | 6 | 1000 | 6000
K733.2 | Allow for breaking up, and temporary and permanent reinstatement of tarmac roads, Rates deemed inclusive of the provision of requisite diversion signage, controls and safety precaution. | m | 10 | 5000 | 50000
K86 | Connections to specifications
Installation of meters including transport, storage and all handling.
K861.1 | Supply and Install Bulk meter DN 160 | nr | 1 | 35467 | 35467
CLASS L : PIPEWORK - SUPPORTS AND PROTECTION,
ANCILLARIES TO LAYING AND EXCAVATION
Excavation of rock as defined in the specifications
L111 | Excavation in rock | m3 | 75 | 1200 | 90000
L112 | Excavation in mass concrete | m3 | 2 | 2000 | 4000
L113 | Excavation in reinforced concrete | m3 | 2 | 2000 | 4000
L114 | Excavation of other artificial hard material | m3 | 1 | 1000 | 1000
L117 | Excavation of natural material below the final Surface and backfilling with concrete | m3 | 1 | 14000 | 14000
Microtunneling
L231.1 | Provision for microtunneling under permanent roads including metal sleeve in accordance with specifications | nr | 2 | 300000 | 600000
Pipe bedding & Surround
L331.1 | Approved imported granular material as per standard drawings | m | 600 | 80 | 48000
Thrust blocks for bends, tees and blank ends. Dimensions of each
block as shown on Drawings
(provision of Concrete, reinforcement and Construction)
L711.1 | Concrete stools and Thrust Blocks (Volume: 0.2-0.5),Nominal bore n.e. 160mm; volume n.e 0.2m3 | nr | 5 | 3000 | 15000
K820 | Marker posts as per drawings
K820.1 | Marker posts for Sliuce Valves inscribed SV | nr | 3 | 1200 | 3600
K820.2 | Ditto but for Washouts inscribed WO | nr | 3 | 1200 | 3600
K820.3 | Ditto but for Air Valve inscribed AV | nr | 4 | 1200 | 4800
K820.4 | Ditto but for Water Main inscribed WM | nr | 3 | 1200 | 3600
| BILL 3 TOTAL CARRIED TO SECTION COLLECTION SHEET |  |  |  | 3270529

## Dayworks
CONSTRUCTION OF BARAKA-CHAKA WATER EXTENSION PROJECT IN NYERI COUNTY
DAYWORKS SCHEDULE
| Item | Description | Unit | Rate Only
1 | Site Agent | hr | 8
2 | General fore man | hr | 8
3 | Foreman | hr | 8
4 | Supervisor | hr | 8
5 | Graded Artisan | hr | 8
6 | Ungraded Artisan | hr | 8
7 | Guard | hr | 8
8 | Welder | hr | 8
9 | Driver | hr | 8
10 | Machine operator | hr | 8
11 | Mason | hr | 8
12 | Plumber | hr | 8
13 | Store keeper | hr | 8
14 | unskilled labour | hr | 8
15 | Plant operator | hr | 8
16 | Site Clerk | hr | 8
17 | Painter | hr | 8
18 | Carpenter | hr | 8
19 | Office assistant | hr | 8
PLANTS AND EQUIPMENT
21 | Welding machine (gasoline powered) | hr | 8
22 | Grinding machine | hr | 8
23 | Generator set | hr | 8
24 | Porker vibrator | hr | 8
25 | Concrete mixer | hr | 8
26 | Dewatering pump | hr | 8
27 | Excavator with bucket | hr | 8
28 | Excavator with Harmmer | hr | 8
29 | Low bed truck | hr | 8
30 | Lorry mounted Crane | hr | 8
31 | Compressor | hr | 8
32 | Backhoe Excavator | hr | 8
33 | Damper | hr | 8
34 | Damping truck | hr | 8
35 | Single cabin pickup | hr | 8
36 | Double cabin pickup | hr | 8
37 | 7 Ton Lorry | hr | 8
38 | 18 Ton Lorry | hr | 8
39 | Pressure testing machine | hr | 8
40 | 45 ton compactor | hr | 8
41 | 5 ton Roller | hr | 8
PIPES & FITTINGS
42 | DN 13 Class 'B' GI pipe | m | 1
43 | DN 50 GI Class 'B' pipe | m | 1
44 | DN 100 class 'B' GI pipe | m | 1
45 | DN 38 Class 'B' GI Pipe | m | 1
46 | DN 90 HDPE PIPE(PN 16) Pipe | m | 1
47 | DN 160 HDPE PIPE(PN16) Pipe | m | 1
48 | DN 110 HDPE PIPE(PN 16) Pipe | m | 1
49 | DN 160 HDPE PIPE(PN 16) Pipe | m | 1
50 | DN 63 HDPE(PN16) | m | 1
51 | DN 50 HDPE (PN 16) | m | 1
52 | DN 75 class 'B' GI Pipe | m | 1
53 | DN 150 CLASS 'D' UPVC pipe | m | 1
54 | DN 200 externally Epoxy coated and internally cement lined pipeline. | m | 1
55 | DN 160 externally Epoxy coated and internally cement lined pipe. | m | 1
56 | DN 110 externally Epoxy coated and internally cement lined pipeline | m | 1
57 | 5/8 '' Bolts and nuts m16 | nr | 1
58 | Red soil | m3 | 1
59 | DN 50 step down coupling | nr | 1
60 | DN75 step down coupling | nr | 1
61 | DN 100 step down coupling | nr | 1
62 | DN 150 step down coupling | nr | 1
63 | DN 200 step down coupling | nr | 1
64 | DN 250 step down coupling | nr | 1
65 | DN 300 step down coupling | nr | 1
66 | DN 50 PN 16 sluice valve | nr | 1
67 | DN75 PN 16 sluice valve | nr | 1
68 | DN 100 PN 16 sluice valve | nr | 1
69 | DN 150 PN 16 sluice valve | nr | 1
70 | DN 200 PN 16 sluice valve | nr | 1
71 | DN 250 PN 16 sluice valve | nr | 1
72 | DN 300 PN 16 sluice valve | nr | 1
73 | Single orifice Aivalve | nr | 1
74 | Type 2 fire hydrant | nr | 1
75 | Type 1 fire hydrant | nr | 1
76 | Marker post | nr | 1
77 | DN 200 x150 Flanged steel taper | nr | 1
78 | DN 250 x200 Flanged steel taper | nr | 1
79 | DN 300 x250 Flanged steel taper | nr | 1
80 | DN 50 Mechanical coupling | nr | 1
81 | DN75 Mechanical coupling | nr | 1
82 | DN 100 Mechanical coupling | nr | 1
83 | DN 150 Mechanical coupling | nr | 1
84 | DN 200 Mechanical coupling | nr | 1
85 | DN 250 Mechanical coupling | nr | 1
86 | DN 300 Mechanical coupling | nr | 1
87 | DN 50 Flanged steel tee. | nr | 1
88 | DN75 Flanged steel tee. | nr | 1
89 | DN 100 Flanged steel tee. | nr | 1
90 | DN 150 Flanged steel tee. | nr | 1
91 | DN 200 Flanged steel tee. | nr | 1
92 | DN 250 Flanged steel tee. | nr | 1
93 | DN 300 Flanged steel tee. | nr | 1
94 | DN 50 Flanged steel spigots. | nr | 1
95 | DN75 Flanged steel spigots | nr | 1
96 | DN 100 Flanged steel spigots. | nr | 1
97 | DN 150 Flanged steel spigots. | nr | 1
98 | DN 200 Flanged steel spigots. | nr | 1
99 | DN 250 Flanged steel spigots. | nr | 1
100 | DN 300 Flanged steel spigots. | nr | 1
101 | DN 50 Steel plain flange. | nr | 1
102 | DN75 Steel plain flange | nr | 1
103 | DN 100 Steel plain flange. | nr | 1
104 | DN 150 Steel plain flange. | nr | 1
105 | DN 200 Steel plain flange. | nr | 1
106 | DN 250 Steel plain flange. | nr | 1
107 | DN 300 Steel plain flange. | nr | 1
108 | DN 50 Flange adaptor | nr | 1
109 | DN75 Flange adaptor | nr | 1
110 | DN 100 Flange adaptor | nr | 1
111 | DN 150 Flange adaptor | nr | 1
112 | DN 200 Flange adaptor | nr | 1
113 | DN 250 Flange adaptor | nr | 1
114 | DN 300 Flange adaptor | nr | 1
115 | DN 50 Bend | nr | 1
116 | DN75 Bend | nr | 1
117 | DN 100 Bend | nr | 1
118 | DN 150 Bend | nr | 1
119 | DN 200 Bend | nr | 1
120 | DN 250 Bend | nr | 1
121 | DN 300 Bend | nr | 1
122 | Marker post | nr | 1
124 | Ballast | ton | 1
125 | River sand | ton | 1
126 | Hard core | m3 | 1
127 | Quarry dust | ton | 1
128 | Cabro blocks | m2 | 1
129 | Hand compactor | hr | 8
133 | Buitumen mix | m3 | 1
134 | Murram | ton | 1
135 | Portland Cement | ton | 1
136 | Grannular materials/Red soil | ton | 1
137 | DN 225 spigot and socket concrete pipe. | m | 10
138 | DN 300 spigot and socket concrete pipe. | m | 10
139 | DN 375 spigot and socket concrete pipe . | m | 10
140 | DN 450 Spigot and socket concrete pipe | m | 10
141 | Y12 Reinforcement bars | m | 10
142 | Y10 Reinforcement bars | m | 10
143 | R 8 Reinforcement bars | m | 10
144 | 150mmx25mm cypress timber | m | 10
145 | 100x25mm cypress timber | m | 10
146 | 25 Ton Heavy duty polyresin manhole access cover | nr | 10
147 | 1050mm Dia preast manhole ring | nr | 10
148 | 1200mm Dia precast concretemanhole ring | nr | 10
149 | 1050mm Dia precast reinforced manhole top slab | nr | 10
150 | Precast concrete 90 Degrees Drop manhole Bend (All sizes) | nr | 10
151 | Precast concrete Drop manhole Tee | nr | 10
152 | BL Internally cement lined steel Pipes. | m | 10
153 | 225mm Precast concrete sandle connector | nr | 10
154 | 225mm Precast concrete wyee junction | nr | 10
155 | Heavy duty ductile iron step iron | nr | 10
157 | 1200mm Dia precast reinforced concrete top slap | m | 10