## RISKS REGISTER 2022-23
CORPORATE RISKS REGISTER FY 2022/2023
INHERENT RISK ASSESMENT | [11 empty] | RISK TREATMENT PLAN |  |  |  |  | RESIDUAL RISK ASSESSMENT
Risk ID | SRATEGIC OBJECTIVE | DEPARTMENTAL OBJECTIVE | RISK | CAUSE / SOURCE | CONSEQUENCE DESCRIPTION | EXISTING CONTROLS | LIKELIHOOD | CONSEQUENCE | RISK SCORE | RISK LEVEL | RISK TREATMENT | ACTIVITIES TO BE DONE | RESOURCES | TIMELINES | STATUS/KPI | RESPONSIBILITY | OBJECTIVE EVIDENCE | LIKELIHOOD | CONSEQUENCE | RISK SCORE | RISK LEVEL | EVALUATION IN EFFECTIVENESS
1 | SO7:Improve service delivery | To maintain ISO 9001:2015 QMS Certification in FY 2022/2023 | Failure to maintain ISO 9001:2015 QMS Certification in FY 2022/2023 | 1. Undefine processes through procedures. 2.Failure to address non-conformities 2. Lack of top management support 3. Budgetary constraints 4. lack of employees' commitment and goodwill. | 1. Withdrawal of QMS Certificate 2. Reduced operational efficiency 3. Reduced brand reputation 3. Loss of stakeholders' trust and goodwill | 1. Pool of trained internal auditors 2. Assignment of clear roles and responsibilities to both MR& DMR 3.Follow up on Non conformities raised/reported 4.Existence and implementation of standard operating procedure 5. Annual QMS budget 6. Management reviews, 7. Surveillance audits 8. Annual Quality audit programmes 9.Regular trainings/sensitizations on ISO implementation. | 2 | 4 | 8 | Medium | Mitigate | 1. Review/develop standard operating procedures for new divisions/sections 2. Undertake adhoc quality audits of processes and implement recommendations 3. Train more auditors and implementers 4. Ehnance follow-ups of identified non- conformities | Finances Human Resorce, office equipment (Furniture, desk, computers/laptops), telephone acces/airtime, stationery | 30th June 2023 | 1. Maintained Certification. 2.No of reviewed/developed standard operating procedures for new divisions/sections 3. No of adhoc quality audits of processes undertaken 4. No of trained auditors and implementers 5. No of non-conformities closed on time | MR/DMR | 1. Reviewed two (2)standard Operating Procedures. 2. conducted two (2) internal Quality audits and One (1) Surveillance Audit. 2. closed ten (10) internal audits NCs and one (1) NC from the external Surveillance Audits. | 1 | 3 | 3 | LOW | The actions to address the risks were effective. Continue monitoring the implementation.
|  | To develop and implement risk management policy framework within all functional areas by 30th June 2023 | Failure to implement the risk management policy framework | 1.Risk management skill gaps among process owners 2. Budgetary constraints 2. Lack of top management support | 1. Delays in achieving perfomance targets | 1. Existence of draft risk management policy framework 2. Establishment of risk management section 3. Trained management team on risk management 4. Existence of risk registers at divisional levels | 2 | 3 | 6 | Medium | Mitigate | 1. Train risk champions from each division 2. Sensitize all staff on risk management | Finances Human Resorce, office equipment (Furniture, desk, computers/laptops), telephone acces/airtime, stationery | 30th June 2023 | 1. No of Trained risk champions from each division 2. No of staff sensitized |  | Developed Risk Management Policy Framework . | 2 | 2 | 4 | LOW | The actions to address the risks were effective. Continue monitoring the implementation.
1 | S07- Improve Service Delivery | To provide assurance that the Agency’s assets are safeguarded and internal control systems are strengthened by conducting 100% internal audits as per the approved audit plan in the financial year. | Inability to complete all audit activities as per Audit Plan due to unplanned activities and unavailability of auditees | 1.Adhoc investigations 2. Lack of co-operation from management 3. High workload of the auditees | 1. The Agency may not be able to get the overall risk management status. 2. The Agency may not get acurate information about the status of Internal Control System. 3. Inability of the Board to make informed decisions to mitigate the risks, strengthen the Internal Control System and Governance. | 1. Effective planning of the audit plan. 2. Dissemination of the audit notification/programme to the departmental/divisional heads in time. 3. Holding entry and exit meetings where resource needs and scope are clearly spelt out. 4. Working overtime to complete the workplan. | 3 | 2 | 6 | MEDIUM | MITIGATE | 1. Request for an additional staff 2. Enhancing capacity of existing staff 3. Sensitizing the management on the role and importance of internal audits and recommendations | 1. Audit management software and Computer-Assisted Audit Techniques (CAATs) 2. Human Resource 3. Office equipment (Furniture, desk, computers/laptops), 4. Telephone acces/airtime, motorvehicle, stationery | 30th June 2023 | 1. No. of system audits conducted. 2. No of responses received from the auditees. 3. No of rejoinders. | MIAA | 1 No. Intern engaged within the financial year. | 4 | 2 | 8 | MEDIUM | The controls were not effective and the risks have gone up since.
| SO 11 - Enhance Human Resource Capacity | To conduct one (1) employee satisfaction survey by June 2023 | Failure to conduct employee satisfaction survey due to inadequate funding | Failure by the government to release funding due to austerity measures | Employee needs/requirements may not be identified | Annual Budget proposals | 3 | 3 | 9 | MEDIUM | mitigate | 1.Maintain and monitor the existing controls 2. 1. Mobilisation for release of funding by the government | Human Resource, office equipment (Furniture, desk, computers/laptops), telephone acces/airtime, stationery, Budget | 30th June 2023 | Employee satisfaction survey done | MHRMA |  | 3 | 3 | 9 | MEDIUM | Action to treat the risk was not effective. Austerity measures were implemented throughout 2022-2023
|  | To conduct one (1) work environment survey by June 2023 | Failure to conduct work environment survey due to inadequate funding | Failure by the government to release funding due to austerity measures | Work environment needs/requirements may not be identified | Annual Budget proposals | 3 | 3 | 9 | MEDIUM | MITIGATE | 1. Monitor the existing controls 2. Mobilisation for release of funding by the government | Human Resorce, office equipment (Furniture, desk, computers/laptops), telephone acces/airtime, stationery, Budget | 30th June 2023 | Employee work environment satisfaction report |  |  | 3 | 3 | 9 | MEDIUM | Action to treat the risk was not effective. Austerity measures were implemented throughout 2022-2023
|  | To undertake one (1)training needs assessment and implement recommendations | Failure to undertake Training Needs Assessment due to unavailability of funding. | austerity measures | 1. Failure to identify the relevant training needs 2. Requirement for staff training will not be prioritized | 1. Annual Budget proposals, 2.Training programmes to be undertaken | 2 | 4 | 8 | MEDIUM | MITIGATE | 1. Monitor the existing controls 2. Continue mobilising for funding | Human Resorce, office equipment (Furniture, desk, computers/laptops), telephone acces/airtime, stationery, Budget | 30th June 2023 | TNA Report An approved training plan |  |  | 1 | 4 | 4 | LOW | The controls were effective
|  | Develop And Implement mentorship and coaching plan and implement for Technical Department by December 2023 | Failure to undertake mentorship and coaching | Due to Unavailability of mentors and mentees; workloads | 1. Failure to have succession plans 2. Loss of institution memory | 1. Existing policy on mentorship and coaching 2. 2.Availability of Experienced professionals to mentor graduate Employees 3. Availability of trained mentors by PSC in the Technical Department | 1 | 4 | 4 | LOW | Accept | 1.Train more Mentors 2.Sensitize Staff on mentorship and coaching policy, 3.Motivate the mentors | Human Resorce, office equipment (Furniture, desk, computers/laptops), telephone acces/airtime, stationery, Training Budget | 30th June 2023 | 1.number of mentorship engagements 2.Training reports, sensitization reports/attendance | MHRMA / CMTS |  | 1 | 4 | 4 | LOW | The controls were effective
|  | Train Management staff on Performance Management System by June 2023 |  | Inadequate budget due to austerity measures | 1. Lack of objectivity in staff perfromance appraisal. | 1. Sensitization on Performance Appraisal Procedure | 3 | 2 | 6 | MEDIUM | MITIGATE | Train the committee on Performance Management, | Budget, Time | 30th June 2023 | Training report, | MHRMA |  | 3 | 2 | 6 | MEDIUM | The control was not effective
|  | Provision of staff welfare facilities by 30th June 2023 | Failure to provide staff welfare facilities | Inadequate funding | Dissatisfied employee, staff turn-over, absenteeism | Annual Budget proposals | 1 | 4 | 4 | LOW | ACCEPT | No additional measures required. Continue monitoring the existing control | Human Resorce, office equipment (Furniture, desk, computers/laptops), telephone acces/airtime, stationery, Budget | 30th June 2023 | Availability of staff welfare facilities |  | Existence of Contracts; utilization reports, | 4 | 1 | 4 | LOW | Monitor the controls
1 | SO4- Improve Financial Sustainability | To mobilize KES 300 Million for the development of National Public Water and Sanitation Works in the Financial Year 2022/2023. | Failureto mobilize KES 300 Million for the development of National Public Water and Sanitation due to reduced support by development partners | 1. Project Concept Notes(PCN) and Project financing proposals for funding that don't meet the development partners' requirements 2. failure to adhere to requirements of the existing/previous development partners' funding policy and guidelines 3. Delays in Resource Mobilization activities due to pandemic-related Issues 4. Changes in government policies/guidelines that freeze the implementation of new projects 5. Government restrictions and ceiling on borrowing 7. Delay in PCN approvals 8. Inability to market the Concept Paper and Project proposal for funding. | 1. Inadequate funding to implement activities from the strategic plan 2. Delayed projects 3. Dissatisfied stakeholders 4 Reduced operational efficiency . | 1. Monitor compliance with signed Financing Agreements and MOUs 2 Monitoring adherence to requirements of the development partners' funding policy and guidelines 3. Incorporating New project concept paper and project financing proposal to the Parent Ministry for future funding consideration in the Medium Term Expenditure Framework (MTEF) 4. Attending training on the Development of quality concept papers conducted by the parent ministry in collaboration with the National Treasury 5. Lobbying with TNT,Parent Ministry and development partners | 3 | 4 | 12 | Medium | Mitigate | 1. Develop New project PCN, Feasibility and submit for approval. 3. Building Capacity for staff on advocacy and networking 4. Enhance Lobbying with TNT, Parent Ministry, and development partners 5. Appointment of Project Committee to review the PCN before submission for approval by the MoWSI and TNT | 1. Time 2. Finances 3. Human Resource | 30th June 2023 | 1. Amount of funds mobilized through RM strategy activities 2. No. of the new project, PCN developed and submitted for approval 3. No. of staff trained in advocacy and networking 4. No. of PCN reviewed by the project committee | CMF&RM | PCN Developed for SWED Fund, KOAFEC and NUWASP(ADB) | 2 | 4 | 8 | Medium | Mitigation measures Effective
2 | SO5- Enhance partnership and Collaboration | To establish 2 N0. partnerships and collaborations in the Financial Year 2022/2023 | Failure to establish 2 N0. partnerships and collaborations due to lack of supportive legislation | 1. Lack of political goodwill 2. Poor institution reputation | 1. Inadequate funding 2. lack of new programmes 3.Dissatisfied stakeholders | 1. Holding meetings with potential partners 2. Compliance with laws and regulations | 3 | 3 | 9 | Medium | Mitigate | 1. Research on the interest of existing and New development partners in the Water sector through visiting their embassy or Desktop research. 2. Engage the private sector in water infrastructure development through PPP after legistlation. Lobbying with Parliamentary Accounts Commiittee, Ministry of Water, Sanitation and Irrigation | 1. Time 2. Finances 3. Human Resource | 30th June 2023 | 1. No. of Partnership and Collaboration established 2. No. of projects initiated through PPPs | CMF&RM | PPPs Expression of Interest | 2 | 3 | 6 | Medium | Mitigation measures Effective
1 | Improve service delivery | To increase the percentage of processed payments requests by internal customers within 5 working days from 90% to 97% . | Failure to achieve 97% payment processing within 5 working days due to lack of Funds and incomplete documentation | i) Delayed disbursement of allocated funds ii) Unsupported staff claims and imprests iii) Late imprests accounting by staff | i) Demotivated staff ii) Failure to achieve workplan targets iii) Underabsorption of allocated funds | i) Adherance to Finance & Accounts SoPs, PFM Act, Finance Manual , Policy, Government Circulars. ii) Memo to all staff on requirements for imprest application and accounting. iii) Draw reminder letters to the Parent Ministry on disbursement of allocated funds. | 4 | 3 | 12 | Medium | Mitigate | i) Draw reminder letters to the parent ministry on disbursement of allocated funds. ii) Memo to staff on requirements for imprest application and accounting. | Budget, personnel, Strategic Plans development Guidelines, PFM Act 2012,PFMR 2015, Government Circulars, Government Finance Statistic Standards Codes. Payroll summaries and schedules. | 30th June 2023 | Percentage of payments processed on time | CMF&RM | i) Letters to Parent Ministry ii) Memo to Staff | 4 | 4 | 16 | High | Controls were not effective
2 | Improve service delivery | To increase the percentage of processed payments requests by external providers within 30 working days from 90% to 95% . | Failure to achieve 95% payment processing within 30 working days due to lack of Funds and incomplete documentation | i)Delayed disbursement by the Parent Ministry | Delays in payments to Contractors/Consultants/ suppliers, Demotivated Contractors, Bad reputation of the organisation, Penalties on delayed payments, Go slow by the contractorsBad reputation of the Organisation, Complaints & Litigations, Poor workmanship , Project cost overun. | i) Draw reminder letters to the Parent Ministry on disbursement of allocated funds. ii)Adherance to the Finance & Accounts Service Charter , iii) Communication to project Officers and procurement Division on payment processing requirements prior to submission of payment documents. | 4 | 3 | 12 | Medium | Mitigate | i) Draw reminder letters to the parent ministry on disbursement of allocated funds. ii) Communication to project Officers and procurement Division on payment processing requirements prior to submission of payment documents. . | Budget, personnel, Strategic Plans development Guidelines, PFM Act 2012,PFMR 2015, Government Circulars, Government Finance Statistic Standards Codes. Payroll summaries and schedules. | 30th June 2023 | Percentage of payments processed on time | CMF&RM | i) Letters to Parent Ministry ii) Memo to Communication to project Officers and procurement Division . | 4 | 4 | 16 | High | Controls were not effective
3 | Improve Financial Sustainability | To achieve 0% loss of funds through fraud | Loss of funds due to fraud | Lack of staff Integrity,Weak Controls | Organisation objectives not met, Disatisfaction of Stakeholders, Negative reputation | i) Stages of approval, ii) Internal Audit function within the organisation iii) Code of conduct for the organisation.iv) Implementatiom of the fraud and corruption risk mitigation plan. | 1 | 4 | 4 | Low | Maintain
1 | SO7. Improve Service Delivery | Implement ERP and Integration of Processes to increase Automation Level from 64% to 72% by end of Financial Year 2022/2023 | i) Failure to achieve the desired Automation level due to inadequate funding and low user uptake | i) Inadequate funding from exchequer | i) Low operational efficiency level iii) Low customer satisfaction level | i) Budgetting ii.) Adequate technical capacity in the Agency iii.) Procurement plan to engage consultants. iii.) Divisional workplan | 2 | 2 | 4 | MEDIUM | MITIGATE | i). Strict adherance to project completion timelines ii) Proper ERP Change Management and user trainings iii.) Timely preparation of Divisional budget | 1. Personnel 2. Finance 3. Time | 30th June 2023 | i). No of Integrated Systems ii). No of operational ERP modules iii).Percentage of Automation Level iv). No. of acquired PDAs | Manager, ICT | i. Delivery Notes for acquisition of PDAs ii. Integration links iii. Desktop / Web Applications iv. Annual budgets | 2 | 2 | 4 | Low | Controls were effective
2 |  | To handle 100% of customer enquiries and complaints on ICT services as provided in the ICT customer service charter in the Financial Year 2022/2023. | Unresolved customer complaints due to non responsive external providers and internal breakdown of infrastructure | i) Hardware and Software obsoleteness ii.) Late payment of services iii.) Lack of capacity of service provider. | i) Low customer satisfaction level ii) Increased customer complaints | i) ICT Help desk services ii) User Support Register iii) User Support Standard Operating Procedure iv) ICT Policy v.) Contracts with external providers | 1 | 3 | 3 | LOW | Maintain |  | 1. Personnel 2. Time | Quarterly | i. No. of complains received and resolved | Manager, ICT | User log register | 1 | 3 | 3 | Low | Controls were effective
3 |  | To Improve institutional network security through acquisition of 2 No. of network security firewalls in Financial Year 2022/2023 | Loss of Data Confidentiality, Integrity and Availability (CIA) due to unathorised access. | i) Rapid technological advancement ii) Existing rampant cyber crime | i) Compromised data integrity and negative institution's reputation. ii) Disruption in service delivery | i) Use of valid Antivirus Software ii) Use of network security firewalls iii) Sensitization of staff on information security iv) ICT Security Standard Policy | 2 | 3 | 6 | MEDIUM | MITIGATE | i). Ensure adherence on acquisition and implementation of Network Security Firewalls | 1. Personnel 2.F inance 3. Time | 30th June 2023 | i). No. of Acquired Network Security Firewalls ii). No. of operational Network Security Firewall | Manager, ICT | i. Delievery Notes ii. Completion certificate iii. Software and Physical Firewalls | 3 | 3 | 9 | Medium | The controls are working but there are emerging cyber threats that can impact the agency's information security.
1 | SO1- ( Increase access to water and Sanitation Services) | Develop Master Plan Covering the 5 Counties by end of FY 2023/2024 | Failure to develop a comprehensive master plan due to inadequate finance and lack of historical data. | 1.Inadequate funding by Exchequer. 2.Lack of documented information at the County Level. | 1. Dissatisfied stakeholders e.g WSPs and County Governments 2.Poor planning of the Organisational Activities. | 1. Stakeholders engagements forums 2. Establishment of a committte to spearhead the exercise. 3. Budget 4. Work Plan | 3 | 2 | 6 | MEDIUM | MITIGATE | 1. Timely submission of budgets. 2. Continous stakeholders collaboration; while developing the master plan 3. Timely request for staff training on masterplan development. 4. Benchmark with other institutions that have developed Master plan 5. Timely sourcing of the required data. | Human Resource, office equipment (Furniture, desk, computers/laptops), telephone acces/airtime, motorvehicle, stationery | 30th June 2023 | 1. Number of County Master Plans developed. | CMTS | 1. Submitted budget. 2. Minutes for stakeholder engagement. 3. Benchmarking request/benchmarking report. 4. Training request 5. Data requests to relevant stakeholders. | 4 | 2 | 8 | MEDIUM | Controls were not effective.
|  | Develop 3 out of 7 design works that are inclusive of last mile connectivity by end of FY 2023/2024 | Development of designs with inadequate last mile connectivity due to insufficient information on the project objectives. | 1.Inadequate stakeholder engagement before design stage. | 1.Delayed realization of project objectives i.e increased coverage of water and sewer. | 1. Stakeholders engagements 2. Appointment of design teams to carry out the works | 3 | 3 | 9 | MEDIUM | MITIGATE | 1. Timely submission of budgets. | Human Resource, office equipment (Furniture, desk, computer hardware and software), telephone acces/airtime, motorvehicle, stationery, survey equipment | 30th June 2023 | 1. Number of design reports with last mile component. | CMTS | 1.Submitted Budget 2.Data requests to relevant stakeholders. | 2 | 2 | 4 | LOW | Controls were effective
2 | SO5 - ( Enhance partnership and collaborations. | Develop 8 Concept notes for development programmes by the end of FY 2023/2024 | 1.Failure to develop targetted concept notes due to inadequate staff skills. | 1.Inadequate staff with knowledge of preparing concept notes. 2.Lack of internal competence in developing the concept notes. | 1. Not able to get project funding. 2.Bad reputation with Development Partners. 3.Dissatisfied Stakeholders. | 1. Divisional workplans. 2. Budget. | 2 | 4 | 8 | MEDIUM | MITIGATE | 1. Timely planning and allocation of tasks to specific persons. | Human Resource, office equipment (Furniture, desk, computer hardware and software), telephone acces/airtime, motorvehicle, stationery,survey equipment | 30th June 2023 | 1. Number of concept notes developed. | CMTS | 1. Individual workplan or memo to allocate the task. 2. Training request | 2 | 4 | 8 | MEDIUM | Controls were not effective
|  |  | 2. Development of non-compliant concept notes due to varying submission formats and human error. | 1. Lack of internal competence in developing the concept notes. 2. Inadequate information to develop a comprehensive concept note. 3. Inadequate time for preparation and review of concept notes due to strict timelines. | 1. Rejected concept note hence not able to get project funding. 2. Bad reputation with Development Partners. | 1. Induction of the division manager on the MOWI concept note preparation guidelines. | 2 | 4 | 8 | MEDIUM | MITIGATE | 1. Inducting staff training on the MOWI concept note guidelines. 2. Undertaking confirmatory survey/data collection. | Human Resource, office equipment (Furniture, desk, computer hardware and software), telephone acces/airtime, motorvehicle, stationery,survey equipment | 30th June 2023 | 1. Number of compliant concept notes developed. | CMTS | 1.Staff Induction report 2.Request/report for recoinnisance survey. | 3 | 4 | 12 | MEDIUM | Controls were not effective
3 | SO6 - ( Enhance stakeholders participation and engagement) | Undertake Project appraisals for 80% of the approved stakeholders requests by the end of FY 2023/2024 | Failure to undertake Project appraisals for the approved stakeholders requests due to inadequate staff and finance. | 1. Inadequate funding by Exchequer. 2. Inadequate divisional staff establishment as compared to numerous prioritised works with competing urgencies. | 1. Dissatisfied stakeholders, when there is delay in carrying out the appraisals of their project. 2. Delay in design and implementation of potential projects. | 1. Appointment of appraisal teams as requests are received to the division. 2. Budget | 2 | 3 | 6 | MEDIUM | MITIGATE | 1. Establish division document register to track approved requests. 2. Brief rescheduling of ongoing activities to prioritize appraissals. | Human Resource, office equipment (Furniture, desk, computer hardware and software), telephone acces/airtime, motorvehicle, stationery. | 30th June 2023 | 1. Number of Project Appraisal Reports. | CMTS | 1. Division register for request tracking. 2. Overlapping appointment/Re-allocation memo for different tasks. | 3 | 3 | 9 | MEDIUM | Controls were not effective
1 | S01 - To increase access to water supply services | To increase access to water supply services from 58% to 63% by FY2022/2023 by implementing the following: 1. Construction of Chogoria Water Supply Project 2. Construction of Kerugoya Kutus Water Supply Project 3. Construction of Murang'a South Water Supply Project 4. Construction of Murang'a Urban Water Supply Project 5. Construction of Gitije Kandugu Water Supply Project | Delay in project completion due to non-performance of Contractors | 1. Cashflow constraints faced by Contractors 2. Incompetent site staff 3. Inadequate materials, plant and equipment 4. Inclement weather | 1. Cost overruns 2. Dissatisfied stakeholders | 1. Selection of Contractor's based on past performance and conducting of due dilligence 2. Monthly site meetings held to review progress 3. Monitoring and evaluation of progress reports 4. Submission of programme of works by Contractor that is monitored for delay | 4 | 2 | 8 | Medium | Mitigate | 1. Monitoring of Contractor's adherance to programme of works 2. Convening of management meetings 3. Issuance of notices for delay and charging Contractor for delay damages 4. Termination of Contracts | Finances Human resource Transport | 30th June, 2023 | Number of projects completed on time | CMTS | Completed projects | 5 | 4 | 20 | High | Actions were ineffective
|  |  | Delay in project completion due to delayed approvals | 1. Agency delays to make timely applications 2. External institutions delay in granting timely approvals | 1.Cost overruns 2. Dissatisfied stakeholders | 1. Applications are made at Planning and Design phase of the project cycle 2. Internal escalation mechanism that includes follow up meetings, reminders through letters | 3 | 2 | 6 | Medium | Mitigate | 1. Consistent follow up with external Government institutions 2. Close collaboration with Government Delivery Services and MoWSI liaison officers | Finances Human resource Transport | 30th June, 2023 | 1. Number of approvals made on time 2. Number of approvals granted |  | 1. Applications 2. Approvals | 4 | 3 | 12 | Medium | Actions were ineffective
|  |  | Delay in project completion due to delayed disbursement of funds | 1. Inadequate budgetary allocation | 1.Cost overruns 2. Dissatisfied stakeholders | 1. Lobbying for timely allocation and disbursement of funding by the National Treasury and MoWSI 2. Stakeholder Forums (Politicians also invited to forums) | 4 | 2 | 8 | Medium | Mitigate | Follow up with the National Treasury and Ministry of Water, Sanitation and Irrigation | Finances Human resource Transport | 30th June, 2023 | 1. Amount disbursed to the Agency |  | Timely Payments | 4 | 4 | 16 | Medium | Actions were ineffective
|  |  | Failure to achieve targeted consumer connections due to lack of last mile connectivity component of projects | 1. Inadequate budgetary allocation | 1. Loss of revenue 2. Dissatisfied stakeholders 3. Lack of Return on Investment 4. Reduced Operational Efficiency | 1. Adequate Consumer Sensitization and Awareness 2. Lobbying for adequate funding | 4 | 3 | 12 | High | Mitigate | Partner with Counties and Water Service Providers in funding last mile connectivity projects | Finances Human resource Transport | 30th June, 2023 | Number of last mile connectivity projects implemented |  | Last mile connectivity projects implemented | 3 | 3 | 9 | High | Actions were ineffective
|  |  | Completed construction not meeting technical specifications due to inadequate supervision | 1. Inadequate works supervision 2. Poor quality Planning and Design 3. Fraudulent and Collusion practices between the Contractor and works superintendent | 1. Increase in Maintenance Costs 2. Lack of Customer Satisfaction 3. Lack of Ownership by the End User | 1. Adherence toTechnical Specifications 2. Engagement of Competent Officers 3. Inspection and acceptance of works | 2 | 4 | 8 | Medium | Mitigate | Technical staff training/Workshops | Finances Human resource Transport | 30th June, 2023 | Number of trainings done. |  | 1. Training Needs Assessment 2. Trainings undertaken | 4 | 4 | 16 | Medium
2 | S02 - To increase access to sanitation services | To increase access to sanitation services from 8% to 13% by FY2022/2023 by implementing the following: 1. Construction of Kerugoya Kutus Sewerage Project 2. Construction of Chogoria Sewerage Project 3. Construction of Chuka Sewerage Project | Delay in project completion due to non-performance of Contractors | 1. Cashflow constraints faced by Contractors 2. Incompetent site staff 3. Inadequate materials, plant and equipment 4. Inclement weather | 1. Cost overruns 2. Dissatisfied stakeholders | 1. Selection of Contractor's based on past performance and conducting of due dilligence 2. Monthly site meetings held to review progress 3. Monitoring and evaluation of progress reports 4. Submission of programme of works by Contractor that is monitored for delay | 4 | 2 | 8 | Medium | Mitigate | 1. Monitoring of Contractor's adherance to programme of works 2. Convening of management meetings 3. Issuance of notices for delay and charging Contractor for delay damages 4. Termination of Contracts | Finances Human resource Transport | 30th June, 2023 | Number of projects completed on time |  | Completed projects | 5 | 4 | 20 | High
|  |  | Delay in project completion due to delayed approvals | 1. Agency delays to make timely applications 2. External institutions delay in granting timely approvals | 1.Cost overruns 2. Dissatisfied stakeholders | 1. Applications are made at Planning and Design phase of the project cycle 2. Internal escalation mechanism that includes follow up meetings, reminders through letters | 3 | 2 | 6 | Medium | Mitigate | 1. Consistent follow up with external Government institutions 2. Close collaboration with Government Delivery Services and MoWSI liaison officers | Finances Human resource Transport | 30th June, 2023 | 1. Number of approvals made on time 2. Number of approvals granted |  | 1. Applications 2. Approvals | 4 | 3 | 12 | Medium | Actions were ineffective
|  |  | Delay in project completion due to delayed disbursement of funds | 1. Inadequate budgetary allocation | 1.Cost overruns 2. Dissatisfied stakeholders | 1. Lobbying for timely allocation and disbursement of funding by the National Treasury and MoWSI 2. Stakeholder Forums (Politicians also invited to forums) | 4 | 2 | 8 | Medium | Mitigate | Follow up with the National Treasury and Ministry of Water, Sanitation and Irrigation | Finances Human resource Transport | 30th June, 2023 | 1. Amount disbursed to the Agency |  | Timely Payments | 4 | 4 | 16 | Medium | Actions were ineffective
|  |  | Failure to achieve targeted consumer connections due to lack of last mile connectivity component of projects | 1. Inadequate budgetary allocation | 1. Loss of revenue 2. Dissatisfied stakeholders 3. Lack of Return on Investment 4. Reduced Operational Efficiency | 1. Adequate Consumer Sensitization and Awareness 2. Lobbying for adequate funding | 4 | 3 | 12 | High | Mitigate | Partner with Counties and Water Service Providers in funding last mile connectivity projects | Finances Human resource Transport | 30th June, 2023 | Number of last mile connectivity projects implemented |  | Last mile connectivity projects implemented | 3 | 3 | 9 | High
|  |  | Completed construction not meeting technical specifications due to inadequate supervision | 1. Inadequate works supervision 2. Poor quality Planning and Design | 1. Increase in Maintenance Costs 2. Lack of Customer Satisfaction 3. Lack of Ownership by the End User | 1. Adherence toTechnical Specifications 2. Engagement of Competent Officers 3. Inspection and acceptance of works | 2 | 4 | 8 | Medium | Mitigate | Technical staff training/Workshops | Finances Human resource Transport | 30th June, 2023 | Number of trainings done. |  | 1. Training Needs Assessment 2. Trainings undertaken | 4 | 4 | 16 | Medium
3 | S07 - Improve service delivery | Develop contract management policy/framework by FY2022/2023 | Failure to complete development of Contract management policy/framework | 1.Lack of adequate finances | 1. Cost overruns 2. Project delays 3. Legal and regulatory liability | 1. Strict adherance to Standard Operating Procedure for Contract Management 2. Adherance to Contract provisions (technical specifications, BoQs) | 1 | 3 | 3 | Low | Accept | Technical staff training/Workshops | Finances Human resource Transport | 30th June, 2023 | Contract Management Policy/Framework Developed |  | Contract Management Policy/Framework approved | 3 | 4 | 12 | High
| S02-Enhance research,innovation and uptake in technology | Map sixteen (16) water infrastructure in TWWDA area of Jurisdiction in FY 2022/23 | Failure to map all the targeted water infrastructure due to inadequate funding and resources | Inadequate funding by exchequer | Inequity in water and sanitation projects distribution within the Agency area of jurisdiction. Disatisfied stakeholders Poor planning | Existence of TWWDA Strategic Plan and Divisional workplan . GIS unit in place for projects mapping Budget | 4 | 2 | 8 | Medium | Mitigate | 1.Training of staff to address the skills gaps 2 Procurement of modern mapping equipment 3.Seek for more facilitation in terms of funding through proposal writing | Finances, Equipment, Transport, Time and Human Resource | 30th June 2023 | Number of water and sanitation infrastructure mapped |  | Excel data sheet for water facilities(boreholes) mapped in 2022/2023. | 4 | 2 | 8 | Medium | The residual risk is equal to inheret risk therefore the controll measure is ineffective.The in adequate funding has not been addressed.
| S05-Enhance partnership and collaboration | Undertake Technical services and capacity building programmes to twenty (20) Water Service Providers and six (6) community water groups in TWWDA area of jurisdiction in FY 2022/23 . | Failure to undertake Technical Services and capacity building to the County Governments ,WSPs and communities due to inadequate funding | Inadequate funding by exchequer | Low stakeholder confidence in the Agency resulting in negative reputation Dissatisfied stakeholders | Divisional Targets and Workplan in place TWWDA Staff establishment structure in existence Budget | 4 | 2 | 8 | Medium | Mitigate | 1.Seek for more facilitation in terms of funding through proposal writing 2.Engage of external resource persons 3. Request for additional staff at Managerial level 4.To build the capacity of divisional staff in terms of skills | Finances, Equipment, Transport, Time and Human Resource | 30th June 2023 | 1.Number of Technical Services and Capacity Building to Water Services Providers and community water groups undertaken. 2. Capacity building proposals for County Governments, WSPs and communites prepared |  | 1.Issue notes for equipments provided to WSPs. 2.Training report 3. Technical services and Capacity building proposals. | 4 | 2 | 8 | Medium | The residual risk is equal to inheret risk therefore the controll measure is ineffective.The in adequate funding has not been addressed.
| S06-Enhance Stakeholder participation and engagment | Hand over sixteen (16)water projects in TWWDA area of Jurisdiction to WSPs ,communities institutions and undertake impact assessment for the projects in FY 2022/23 | Completed water projects not handed over to the beneficiary users (County Government ,WSPs and communities) due to inadequate stakeholder engagement at the initial planning of the project | 1.Political interference 2.Leadership transistion at County Governments leading to prolonged consultations and delay in execution of activities | Unsustainable water and sanitation projects whose intended objectives will not be achieved | Projects handing over procedure in place | 5 | 2 | 10 | Medium | Mitigate | 1. Enhance stakeholder engagement throughout the project cycle. | Finances, Transport, Time and Human Resource | 30th June 2023 | Number of water and sanitation infrastructure handed over . Number and report of stakeholder engagement forums /meetings conducted | CMTS | 1. Desk review data 2. Field visits reports 3. Stakeholder engagement forums /meetings reports 4. Asset mapping excel sheets and inventory forms. 5. Training reports 6. Projects handing over documentation. | 5 | 2 | 10 | Medium | The residual risk is equal to inheret risk. The projects handing over is a process that is continuance and has not been completed.
| S02- Enhance Research, Innovation and Uptake in Technology | To Conduct 2 No. Research studies on water and sanitation in the FY 2022-2023. | Failure to conduct research study(ies) due to inadequate funding | Inadequate/delayed disbursement of funds | 1. Lack of new innovations in development of water and sanitation infrastructure 2. Use of outdated technology 3. Limited data for evidence based decision making 4. Low brand visibility | 1. Existence of Research policy 2. Engagement of qualified employees 3. Existence of MOU with DeKUT 4.Establishment of Research and Survey Division 5. Procedure for data management and research | 3 | 3 | 9 | High | Mitigate | 1. Implement the research policy 2. Implement the existing MOU with DeKut 3. Initiate more collaborations with other institutes of high learning 4. To benchmark and research on emerging innovation and or technology for implementation. | Budget Personnel ICT equipment/application | 30th June 2023 | Number of research studies conducted | MRSP | No research study conducted | 4 | 3 | 12 | MEDIUM | Measures in place not effective
|  |  | Flawed research studies due to inaccurate data. | 1. Use of unvalidited data collection tools 2. Lack of integrity by data enumerators and analysts 2. Biased data analysis with pre-determined data trends | 1. Misleading research recommendations/ decisions | 1. Extistence of Research policy 2. Existence of MOU with DeKUT 3. Establishment of Research and Survey Division 5. Procedure for data management and research | 2 | 4 | 8 | medium | Mitigate |  |  |  | No of quality research studies conducted |  |  | 1 | 5 | 5 | LOW
|  | To Review and Implement knowledge Management Strategy in FY 2022/2023 | Failure to review and implement the Agency's knowledge management Strategy | 1. Inadequate resources 2. Inadequate skills on knowledge management implementation 3. Inadequate Automated knowledge management 4. Inadequate implementation of seamless knowledge management | 1. Loss of knowledge from staff who leave/ retire from the Agency 2. Operational inefficiencies 3. Reduced employee satisfaction 4.Delays in making informed decisions 5. Undertaking Repetitive Processes 6.Difficulty in finding the required information 7. Poor internal collaborations 8. Low levels of customer satistifaction | 1. Knowledge management policy in place 2. Knowledge management portal in place | 1 | 3 | 3 | Low | Maintain and monitor the controls | 1. Implement the research policy 2. Implement the existing MOU with DeKut 3. Initiate more collaborations with other institutes of high learning 4. To benchmark and research on emerging innovation and or technology for implementation. | Budget Personnel ICT equipment/application | 30th June 2023 | Number of research studies conducted |  | Knowledge management strategy not developed | 4 | 2 | 8 | Medium
|  | To develop a Partnership and Collaboration framework for research in the FY 2022/2023 | Failure to develop research partnership and collaboration framework | 1. Inadequate resources | 1. Poor choice of areas of collaborations 2. Poor choice of Partner(s) in collaboration | 1. Strategic plan in place that support the objective | 1 | 3 | 3 | Low | Maintain and monitor the controls | [5 empty] | No research partnership and collaboration framework developed | 4 | 2 | 8 | Medium
| S07-Improved Service Delivery | To ensure 100% monitoring of corporate annual work plan and perfomance contract for the financial year 2022/2023 | Failure to monitor organizational perfomance due to delsys in submission of divisional reports | 1. Inadequate budget for data collection 2. Lack of support from different functional areas 3. workload | 1. Poorly implemented corporate annual workplan and Strategic Plan | 1. Existence of appoved Strategic Plan 2.Monitoring and reporting tools in place 2. Cascaded Annual and Quarterly Perfromance targets 3. Corporate annual workplan aligned to the Strategic Plan | 1 | 5 | 5 | LOW | Mitigate | 1. Develop and implement M&E framework for projects 2. Undertake annual water and sanitation situtaion survey | Budget Personnel ICT equipment/application | 30th June 2023 | 1. Annual PC score for the Agency 2. Implementation levels of strategic plan activities 3. No of monitoring reports developed |  | Quarterly, mid-year and annual monitoring reports -Quarterly Board Paper reports | 1 | 5 | 5 | LOW | Measures in place are effective
1 | SO7- Improve Service Delivery | 1. To procure 100% based on the approved Procurement Plan by the end of June 2023. | Failure to comply with the Plan due to non-responsiveness/or lack of capacity of External Providers | 1. Inadequate Evaluation and due diligence. | 1. Loss of revenues as a result of time-value of money in the light of time passage 2. Delayed orders/Lengthy Lead-times and Delivery times 3. Dissatisfied stakeholders e.g Users 4. Reduced operational efficiency | 1. Timely drawing of procurement plans based on budgetary estimates 2. Formal communication with the external provider 3. Competitive selection of external providers who can offer lengthy credit facilities 4. Appointment of competent tenders` preparation and evaluation teams 5. Compliance with the PPRA guidelines | 4 | 3 | 12 | MEDIUM | REDUCE/MITIGATE | 1. Consistent enforcement of the existing controls, enhanced adherence to the existing controls 2. Develop a large list of Registered external providers; | Human Resource, office equipment (Furniture, desk, computers/laptops), telephone acces/airtime, motorvehicle, stationery | 30th June 2023 | 1. Number of late deliveries made as at the end of 30th June 2023 | MSCM | MSCM; -Evaluation Committees; Project Implementation/RRI team; Inspection & Acceptance Committee. | 3 | 3 | 9 | MEDIUM | Controls were not fully effective
2 | SO7- Improve Service Delivery | To dispose of all (100%) the identified low-value disposable items by the end of FY 2022-2023 | Failure to dispose due to Non-responsiveness of buyers | 1. Poor condition of the disposable items 2. Inflated prices of the disposables | 1. Accumulation of Obsolete items 2. Storage costs and losses 3. Increased Stores Work-load | 1. Wide circulation of the Disposal adverts 2. Market driven costing of disposables. | 3 | 2 | 6 | MEDIUM | REDUCE/MITIGATE | 1. Consider donating disposables to Public Entities e.g. WSPs | Human Resource, office equipment (Furniture, desk, computers/laptops), telephone acces/airtime, motorvehicle, stationery | 30th June 2023 | Percentage of the low-valued items diposed against the total number of the identified listed disposables. | Gate passes for the disposed items, Receipts for sales |  | 3 | 1 | 3 | Low | Controls are effective
1 | SO3 - Improve Brand Visibility | To Implement ten (10) recommendations of the previous customer satisfaction survey(CSSR) by 30th June 2023 | Failure to implement ten (10) recommendations due to inadequate funding | 1.Delayed disbursment of funds 2. Reduced budgetary allocation | 1. Lower brand image 2. Delayed project implementation 3 Dissatisfied stakeholders | 1. Approved budget 2. CSSR reccommendations implementation matrix 3. Alternative Dispute Resolution - Grievance Redress Committee 4. Timely budgetary allocation 5.Follow up on customer complaints and provide feedback | 1 | 2 | 2 | LOW | Maintain existing controls and monitor | N/A |  |  | 1. Reduced No. of unresolved complaints. 2. Amount allocated for sensitizations 3. No. of stakeholder engagements. 4. Developed communication strategy. 5. Updated knowledge management portal 6.No. of capacity building programs undertaken. 7. Undertaken Team building exercise 8. Established way-leave acquisition policy 9. Developed staff succession plan. 10. Enhanced TWWDA reception area. | HOD'S | CSSR implementation matrix and supporting documents | 1 | 2 | 2 | Low | Existing control measures are effective
|  | To develop and implement Communication strategy (includes branding and image strategy) by 30th June, 2023 | Failure to implement the communiction strategy by 30th June, 2023 due to lack of funds | 1.inadequate funding from Treasury | 1. Low TWWDA visibility 2. Decreased brand awareness among stakeholders | 1. Existence of a Communication and PR function 2. Well mappped stakeholders 3.Approved budgets 4. Divisional work plans | 2 | 2 | 4 | LOW | Maintain existing controls and monitor | N/A |  | 30th June 2023 | 1.Developed communication strategy. 2. Strategy implementation plan | MCC&PR | 1.TWWDA Communication Strategy 2.Mapped stakeholders 3. Divisional Workplans 4. Approved budgets | 1 | 3 | 3 | Low | Existing control measures are effective
|  | To Undertake three (3) Corporate Social Responsibility initiatives by 30th June 2023 | Failure to Undertake three (3) Corporate Social Responsibility initiatives by 30th June 2023 due to Lack of funds |  | 1. Poor Organizational image 2. Low stakeholder regard of TWWDA | 1. TWWDA CSR Policy 2.Approved annual budget. 3. Annual workplan 4. Quarterly progress reports | 1 | 3 | 3 | LOW | Maintain existing controls and monitor | N/A |  | 30th June 2023 | No. of CSR activities undertaken | MCC&PR | 1. TWWDA CSR Policy 2. Board Papers 3. CSR reports | 1 | 3 | 3 | LOW | Existing control measures are effective
2 | SO5 - Enhance Partnerships and collaborations | Conduct one annual water and sanitation situation conference by 30th June 2023 | Failure to conduct one annual water and sanitation situation conference due to lack of funds and competing activities within TWWDA. | 1. Competing projects within the Agency affecting the budget allocation 2. Heavy workload among TWWDA staff that affect the availability of the required team | 1.Project prioritization challenges for different regions | 1. Approved budget 2. Annual workplan 3. Quarterly progress reports | 1 | 3 | 3 | Low | Maintain existing controls and monitor | N/A |  | 30th June 2023 | Annual water and sanitation situation conference held | MCC&PR | Draft stakeholder event management framework | 4 | 2 | 8 | Medium | Existing control measures are ineffective
| SO6 - Enhance Stakeholder Participation and Engagement | To Develop and implement one Community/stakeholder engagement strategy by 30th June 2023 | Lack of Community/stakeholder commitment | 1.Delayed disbursment of funds 2. Reduced budgetary allocation 3. Negative political interferance | 1. Slow project implementation 2. Negaive TWWDA brand | 1. Existence of a Communication and PR function 2.Well mapped of stakeholders. 3. Regular meetings with relevant communities, WSPs and County Governments | 1 | 4 | 4 | Low | Maintain existing controls and monitor | N/A |  | 30th June 2023 | No. of Community/stakeholder engagements | MCC&PR | 1. TWWDA stakeholder engagement strategy 2. Mapped stakeholders 3. Stakeholder engagement reports. | 1 | 4 | 4 | Low | Existing control measures are effective
|  | Undertake climate change, adaptation and mitigation programmes by planting minimum 22,000 trees in the FY 2022/2023 | Failure to plant 22,000 trees within the FY 2022/2023 due to unfavourable weather conditions | 1. Unpredictable weather patterns | 1.Deteriorating natural resources in our area of jurisdiction 2.Reduced stakeholder engagement | 1. Approved annual budget 2. Regualr stakeholder engagement, 3.Support of TWWDA Board and Management, | 1 | 3 | 3 | LOW | Maintain existing controls and monitor | N/A |  | 30th June 2023 | Minimum 22,000 trees planted |  | 1. Tree planting reports 2. Divisional Work plans 3. Approved budgets | 1 | 3 | 3 | Low | Existing control measures are effective

## RISKS REGISTER 2023-24
CORPORATE RISKS REGISTER FY 2023/2024
INHERENT RISK ASSESMENT | [11 empty] | RISK TREATMENT PLAN |  |  |  |  | RESIDUAL RISK ASSESSMENT
Risk ID | STRATEGIC OBJECTIVE | DEPARTMENTAL OBJECTIVE | RISK | CAUSE / SOURCE | CONSEQUENCE DESCRIPTION | EXISTING CONTROLS | LIKELIHOOD | CONSEQUENCE | RISK SCORE | RISK LEVEL | RISK TREATMENT | ADDITIONAL MEASURES/ACTIVITIES TO BE DONE | RESOURCES | TIMELINES | STATUS/KPI | RESPONSIBILITY | LIKELIHOOD | CONSEQUENCE | RISK SCORE | RISK LEVEL | OBJECTIVE EVIDENCE | EVALUATION EFFECTIVENESS | RESPONSIBILITY /OWNER
1 | SO7:Improve service delivery | To maintain ISO 9001:2015 QMS Certification in FY 2023/2024 | Failure to maintain ISO 9001:2015 QMS Certification in FY 2023/2024 | 1. Undefine processes through procedures. 2.Failure to address non-conformities 2. Lack of top management support 3. Budgetary constraints 4. lack of employees' commitment and goodwill. | 1. Withdrawal of QMS Certificate 2. Reduced operational efficiency 3. Reduced brand reputation 3. Loss of stakeholders' trust and goodwill | 1. Pool of trained internal auditors 2. Appointment of MR& DMR 3.Follow up on con- conformities raised/reported 3.Existence of standard operating procedure 4. Annual QMS training projections 6. Annual QMS budget 7. Management reviews, 8. Surveillance audits 9. Annual Internal Quality audit programmes 10.Regular trainings/sensitizations on ISO implementation. | 1 | 3 | 3 | LOW | Monitor and control | 1. Review/develop standard operating procedures for new divisions/sections 2. Undertake adhoc quality audits of processes and implement recommendations 3. Train more auditors and implementers 4. Ehnance follow-ups of identified non- conformities | Finances Human Resorce, office equipment (Furniture, desk, computers/laptops), telephone acces/airtime, stationery | 30th June 2024 | 1. No of reviewed/developed standard operating procedures for new divisions/sections 2. No of adhoc quality audits of processes undertaken 3. No of trained auditors and implementers 4. No of non-conformities closed on time | MR/DMR
|  | To implement risk management framework within all functional areas by 30th June 2024 | Failure to implement risk management framework within all functional areas | 1.Risk management skill gaps among process owners 2. Budgetary constraints 2. Lack of top management support | 1. Delays in achieving perfomance targets | 1. Existence of draft risk framework 2. Establishment of risk management section 3. Trained management team on risk management 4. Existence of draft risk registers at divisional levels | 2 | 2 | 4 | LOW | Monitor and control | 1. Train risk champions from each division 2. Sensitize all staff on risk management | Finances Human Resorce, office equipment (Furniture, desk, computers/laptops), telephone acces/airtime, stationery | 30th June 2024 | 1. No of Trained risk champions from each division 2. No of staff sensitized
| S02-Enhance research,innovation and uptake in technology | Map forty (40) water projects in TWWDA area of Jurisdiction in FY 2023/2024 | Failure to map all the targeted water infrastructure due to inadequate funding and resources | Inadequate funding by exchequer | Inequity in water and sanitation projects distribution within the Agency area of jurisdiction. Disatisfied stakeholders Poor planning | Existence of TWWDA Strategic Plan and Divisional workplan . GIS unit in place for projects mapping Budget | 4 | 2 | 8 | Medium | Monitor and control | 1.Training of staff to address the skills gaps 2 Procurement of modern mapping equipment 3.Seek for more facilitation in terms of funding through proposal writing 4. Enhance collaboration with Technical planning division on mapping | Finances, Equipment, Transport, Time and Human Resource | 30th June 2024 | Number of water facilities (boreholes) mapped | CMTS
| S05-Enhance partnership and collaboration | Undertake Technical services and capacity building programmes to twenty (20) Water Service Providers and six (6) community water groups in TWWDA area of jurisdiction in FY 2023/24 . | Failure to undertake Technical Services and capacity building to the County Governments ,WSPs and communities due to inadequate funding | Inadequate funding by exchequer | Low stakeholder confidence in the Agency resulting in negative reputation Dissatisfied stakeholders | Divisional Targets and Workplan in place TWWDA Staff establishment structure in existence Budget | 4 | 2 | 8 | Medium | Monitor and control | 1.Seek for more facilitation in terms of funding through proposal writing 2.Engage of external resource persons 3. Request for additional staff at Managerial level 4.To build the capacity of divisional staff in terms of skills | Finances, Equipment, Transport, Time and Human Resource | 30th June 2024 | 1.Number of Technical Services and Capacity Building to Water Services Providers and community water groups undertaken. 2. Capacity building proposals for County Governments, WSPs and communites prepared | CMTS
| S06-Enhance Stakeholder participation and engagment | Hand twenty-five (25) water projects in TWWDA area of Jurisdiction to WSPs, communities, institutions and undertake impact assessment for the projects in FY 2023/2024 | Completed water projects not handed over to the beneficiary users (County Government ,WSPs and communities) due to inadequate stakeholder engagement at the initial planning of the project | 1.Political interference 2.Leadership transistion at County Governments leading to prolonged consultations and delay in execution of activities | Unsustainable water and sanitation projects whose intended objectives will not be achieved | Projects handing over procedure in place | 5 | 2 | 10 | Medium | Monitor and control | 1. Enhance stakeholder engagement throughout the project cycle. 2.Enhance collaboration with Water and Sanitation Infrastrature division on completed projects ready for handing over. | Finances, Transport, Time and Human Resource | 30th June 2024 | Number of water and sanitation infrastructure handed over . Report of stakeholder engagement forums /meetings conducted | CMTS
| SO1- ( Increase access to water and Sanitation Services) | Develop Master Plan Covering the 5 Counties by end of FY 2023/2024 | Failure to develop a comprehensive master plan due to inadequate finance and lack of historical data. | 1.Inadequate funding by Exchequer. 2.Lack of documented information at the County Level. | 1. Dissatisfied stakeholders e.g WSPs and County Governments 2.Poor planning of the Organisational Activities. | 1. Timely submission of budgets. 2. Continous stakeholders collaboration; while developing the master plan 3. Timely request for staff training on masterplan development. 4. Benchmark with other institutions that have developed Master plan 5. Timely sourcing of the required data. | 4 | 2 | 8 | MEDIUM | Monitor and control | 1. Timely submission of budgets and lobbying for timely facilitation. 2. Continuous stakeholders collaboration; while developing the master plan 3. Benchmark with other institutions that have developed Master plan 4. Timely sourcing of the required data. 5. Close follow-up of appointed Committee on their mandate with timely targets. 6. Desktop studies on existing information. | Human Resource, office equipment (Furniture, desk, computers/laptops), telephone acces/airtime, motorvehicle, stationery | 30th June 2024 | 1. Number of County Master Plans developed. | CMTS
|  | Develop 3 out of 7 design works that are inclusive of last mile connectivity by end of FY 2023/2024 | Development of designs with inadequate last mile connectivity due to insufficient information on the project objectives. | 1.Inadequate stakeholder engagement before design stage. | 1.Delayed realization of project objectives i.e increased coverage of water and sewer. | 1. Timely submission of budgets. | 2 | 2 | 4 | LOW | Monitor and control | 1. Maintain existing controls and monitor. | Human Resource, office equipment (Furniture, desk, computer hardware and software), telephone acces/airtime, motorvehicle, stationery, survey equipment | 30th June 2024 | 1. Number of design reports with last mile component. | CMTS
| SO5 - ( Enhance partnership and collaborations. | Develop 8 Concept notes for development programmes by the end of FY 2023/2024 | 1.Failure to develop targetted concept notes due to inadequate staff skills. | 1.Inadequate staff with knowledge of preparing concept notes. 2.Lack of internal competence in developing the concept notes. | 1. Not able to get project funding. 2.Bad reputation with Development Partners. 3.Dissatisfied Stakeholders. | 1. Timely planning and allocation of tasks to specific persons. | 2 | 4 | 8 | MEDIUM | Monitor and control | 1. Timely planning and allocation of tasks to specific persons. 2. Conducting staff training on the MOWI concept note guidelines | Human Resource, office equipment (Furniture, desk, computer hardware and software), telephone acces/airtime, motorvehicle, stationery,survey equipment | 30th June 2024 | 1. Number of concept notes developed. | CMTS
|  |  | 2. Development of non-compliant concept notes due to varying submission formats and human error. | 1. Lack of internal competence in developing the concept notes. 2. Inadequate information to develop a comprehensive concept note. 3. Inadequate time for preparation and review of concept notes due to strict timelines. | 1. Rejected concept note hence not able to get project funding. 2. Bad reputation with Development Partners. | 1. Inducting staff training on the MOWI concept note guidelines. 2. Undertaking confirmatory survey/data collection. | 3 | 4 | 12 | MEDIUM | Monitor and control | 1. Staff training on the MOWSI concept note guidelines. 2. Undertaking confirmatory survey/data collection. 3. Creation of a database of various concept note formats. | Human Resource, office equipment (Furniture, desk, computer hardware and software), telephone acces/airtime, motorvehicle, stationery,survey equipment | 30th June 2024 | 1. Number of compliant concept notes developed. | CMTS
| SO6 - ( Enhance stakeholders participation and engagement) | Undertake Project appraisals for 80% of the approved stakeholders requests by the end of FY 2023/2024 | Failure to undertake Project appraisals for the approved stakeholders requests due to inadequate staff and finance. | 1. Inadequate funding by Exchequer. 2. Inadequate divisional staff establishment as compared to numerous prioritised works with competing urgencies. | 1. Dissatisfied stakeholders, when there is delay in carrying out the appraisals of their project. 2. Delay in design and implementation of potential projects. | 1. Establish division document register to track approved requests. 2. Brief rescheduling of ongoing activities to prioritize appraissals. | 3 | 3 | 9 | MEDIUM | Monitor and control | 1. Establish division document register to track approved requests. 2. Brief rescheduling of ongoing activities to prioritize appraissals. 3. Hire more interns/Extend their contracts. 4. Utilise other Technical staff in WSI Division who are within the project vicinity. | Human Resource, office equipment (Furniture, desk, computer hardware and software), telephone acces/airtime, motorvehicle, stationery. | 30th June 2024 | 1. Number of Project Appraisal Reports. | CMTS
| S07- Improve Service Delivery | To provide assurance that the Agency’s assets are safeguarded and internal control systems are strengthened by conducting 100% internal audits as per the approved audit plan in the financial year. | Inability to complete all audit activities as per Audit Plan due to unplanned activities and unavailability of auditees | Internal (process) | 1.Adhoc investigations 2. Lack of co-operation from management 3. High workload of the auditees | 1. The Agency may not be able to get the overall risk management status. 2. The Agency may not get acurate information about the status of Internal Control System. 3. Inability of the Board to make informed decisions to mitigate the risks, strengthen the Internal Control System and Governance. | 4 | 2 | 8 | MEDIUM | Monitor and control | Engage an intern in the daily activities | 1. Audit management software and Computer-Assisted Audit Techniques (CAATs) 2. Human Resource 3. Office equipment (Furniture, desk, computers/laptops), 4. Telephone acces/airtime, motorvehicle, stationery | 30th June 2024 | 1. No. of system audits conducted. 2. No of responses received from the auditees. 3. No of rejoinders. | MIAA
| Improve service delivery | To increase the percentage of processed payments requests by internal customers within 5 working days from 90% to 97% . | Failure to achieve 97% payment processing within 5 working days due to lack of Funds and incomplete documentation | i) Delayed disbursement of allocated funds ii) Unsupported staff claims and imprests iii) Late imprests accounting by staff | i) Demotivated staff ii) Failure to achieve workplan targets iii) Underabsorption of allocated funds | i) Adherance to Finance & Accounts SoPs, PFM Act, Finance Manual , Policy, Government Circulars. ii) Memo to all staff on requirements for imprest application and accounting. iii) Draw reminder letters to the Parent Ministry on disbursement of allocated funds. | 4 | 4 | 16 | High | Monitor and control | Maintain the existing controls and monitor | Budget, personnel, Strategic Plans development Guidelines, PFM Act 2012,PFMR 2015, Government Circulars, Government Finance Statistic Standards Codes. Payroll summaries and schedules. | 30th June 2024 | Percentage of payments processed on time | CMF&RM
| Improve service delivery | To increase the percentage of processed payments requests by external providers within 30 working days from 90% to 95% . | Failure to achieve 95% payment processing within 30 working days due to lack of Funds and incomplete documentation | i)Delayed disbursement by the Parent Ministry | Delays in payments to Contractors/Consultants/ suppliers, Demotivated Contractors, Bad reputation of the organisation, Penalties on delayed payments, Go slow by the contractorsBad reputation of the Organisation, Complaints & Litigations, Poor workmanship , Project cost overun. | i) Draw reminder letters to the Parent Ministry on disbursement of allocated funds. ii)Adherance to the Finance & Accounts Service Charter , iii) Communication to project Officers and procurement Division on payment processing requirements prior to submission of payment documents. | 4 | 4 | 16 | High | Monitor and control | Maintain the existing controls and monitor | Budget, personnel, Strategic Plans development Guidelines, PFM Act 2012,PFMR 2015, Government Circulars, Government Finance Statistic Standards Codes. Payroll summaries and schedules. | 30th June 2024 | Percentage of payments processed on time
| Improve Financial Sustainability | To achieve 0% loss of funds through fraud | Loss of funds due to fraud | Lack of staff Integrity,Weak Controls | Organisation objectives not met, Disatisfaction of Stakeholders, Negative reputation
| S02- Enhance Research, Innovation and Uptake in Technology | To Conduct 2 No. Research studies on water and sanitation in the FY 2023-2024. | Failure to conduct research study(ies) due to inadequate funding | Inadequate/delayed disbursement of funds | 1. Lack of new innovations in development of water and sanitation infrastructure 2. Use of outdated technology 3. Limited data for evidence based decision making 4. Low brand visibility | 1. Existence of Research policy 2. Engagement of qualified employees 3. Existence of MOU with DeKUT 4.Establishment of Research and Survey Division 5. Procedure for data management and research | 4 | 3 | 12 | Medium | Monitor and control | 1. Active Mobilization of funding for research studies 2. Initiate more collaborations with other institutes of high learning 3. To benchmark and research on emerging innovation and (or) technology for implementation. | Budget Personnel ICT equipment/application | 30th June 2024 | Number of research studies conducted | MRSP
|  |  | Flawed research studies due to inaccurate data. | 1. Use of unvalidited data collection tools 2. Lack of integrity by data enumerators and analysts 2. Biased data analysis with pre-determined data trends | 1. Misleading research recommendations/ decisions | 1. Extistence of Research policy 2. Existence of MOU with DeKUT 3. Establishment of Research and Survey Division 5. Procedure for data management and research | 1 | 5 | 5 | Low | MAINTAIN | 1. Train data collectors and researchers at the beginning of a research activity 2. Timely planning of intended research activities |  |  | No of quality research studies conducted
|  | To Review and Implement knowledge Management Strategy in FY 2023/2024 | Failure to review and implement the Agency's knowledge management Strategy | 1. Inadequate resources 2. Inadequate skills on knowledge management implementation 3. Inadequate Automated knowledge management 4. Inadequate implementation of seamless knowledge management | 1. Loss of knowledge from staff who leave/ retire from the Agency 2. Operational inefficiencies 3. Reduced employee satisfaction 4.Delays in making informed decisions 5. Undertaking Repetitive Processes 6.Difficulty in finding the required information 7. Poor internal collaborations 8. Low levels of customer satistifaction | 1. Knowledge management policy in place 2. Knowledge management portal in place | 4 | 2 | 8 | Medium | Monitor and control | 1. Timely planning for consideration in budgetary allocation | Budget Personnel ICT equipment/application
|  | To develop a Partnership and Collaboration framework for research in the FY 2022/2023 | Failure to develop research partnership and collaboration framework | 1. Inadequate resources | 1. Poor choice of areas of collaborations 2. Poor choice of Partner(s) in collaboration | 1. Strategic plan in place that support the objective | 4 | 2 | 8 | Medium | Monitor and control | 1. Develop and implement M&E framework for projects 2. Early lobbying for budgetary allocation |  |  | 1. Annual PC score for the Agency 2. Implementation levels of strategic plan activities 3. No of monitoring reports developed
2 | S07-Improved Service Delivery | To ensure 100% monitoring of corporate annual work plan and perfomance contract for the financial year 2022/2023 | Failure to monitor organizational perfomance due to delsys in submission of divisional reports | 1. Inadequate budget for data collection 2. Lack of support from different functional areas 3. workload | 1. Poorly implemented corporate annual workplan and Strategic Plan | 1. Existence of appoved Strategic Plan 2.Monitoring and reporting tools in place 2. Cascaded Annual and Quarterly Perfromance targets 3. Corporate annual workplan aligned to the Strategic Plan | 1 | 5 | 5 | Low | MAINTAIN |  | Budget Personnel ICT equipment/application
1 | SO7. Improve Service Delivery | Implement ERP and Integration of Processes to increase Automation Level from 64% to 72% by end of Financial Year 2022/2023 | i) Failure to achieve the desired Automation level due to inadequate funding and low user uptake | i) Inadequate funding from exchequer | i) Low operational efficiency level iii) Low customer satisfaction level | i) Budgetting ii.) Adequate technical capacity in the Agency iii.) Procurement plan to engage consultants. iii.) Divisional workplan | 2 | 2 | 4 | Low | MAINTAIN | Maintain existing controls and monitor | 1. Personnel 2.F inance 3. Time | 30th June 2024 |  | Manager, ICT
2 |  | To handle 100% of customer enquiries and complaints on ICT services as provided in the ICT customer service charter in the Financial Year 2022/2023. | Unresolved customer complaints due to non responsive external providers and internal breakdown of infrastructure | i) Hardware and Software obsoleteness ii.) Late payment of services iii.) Lack of capacity of service provider. | i) Low customer satisfaction level ii) Increased customer complaints | i) ICT Help desk services ii) User Support Register iii) User Support Standard Operating Procedure iv) ICT Policy v.) Contracts with external providers | 1 | 3 | 3 | Low | MAINTAIN |  |  |  |  | Manager, ICT
3 |  | To Improve institutional network security through acquisition of 2 No. of network security firewalls in Financial Year 2022/2023 | Loss of Data Confidentiality, Integrity and Availability (CIA) due to unathorised access. | i) Rapid technological advancement ii) Existing rampant cyber crime | i) Compromised data integrity and negative institution's reputation. ii) Disruption in service delivery | i) Use of valid Antivirus Software ii) Use of network security firewalls iii) Sensitization of staff on information security iv) ICT Security Standard Policy | 3 | 3 | 9 | Medium | Monitor and control | i). Establishment of Online backup solution |  |  | i.) Stored Data in the cloud | Manager, ICT
1 | SO 11 - Enhance Human Resource Capacity | To conduct one (1) employee satisfaction survey by June 2023 | Failure to conduct employee satisfaction survey due to inadequate funding | Failure by the government to release funding due to austerity measures | Employee needs/requirements may not be identified | Annual Budget proposals | 3 | 3 | 9 | MEDIUM | Monitor and control | 1.Maintain and monitor the existing controls 2. Enhance mobilisation strategies for release of funding by the government | Human Resource, office equipment (Furniture, desk, computers/laptops), telephone acces/airtime, stationery, Budget | 30th June 2024 | Employee satisfaction survey done | MHRMA
|  | To conduct one (1) work environment survey by June 2023 | Failure to conduct work environment survey due to inadequate funding | Failure by the government to release funding due to austerity measures | Work environment needs/requirements may not be identified | Annual Budget proposals | 3 | 3 | 9 | MEDIUM | Monitor and control | 1. Monitor the existing controls 2. Enhance mobilisation for release of funding by the government | Human Resorce, office equipment (Furniture, desk, computers/laptops), telephone acces/airtime, stationery, Budget |  | Employee work environment satisfaction report
|  | To undertake one (1)training needs assessment and implement recommendations | Failure to undertake Training Needs Assessment due to unavailability of funding. | austerity measures | 1. Failure to identify the relevant training needs 2. Requirement for staff training will not be prioritized | 1. Annual Budget proposals, 2.Training programmes to be undertaken | 1 | 4 | 4 | LOW | MAINTAIN |  | Human Resorce, office equipment (Furniture, desk, computers/laptops), telephone acces/airtime, stationery, Budget |  | TNA Report An approved training plan
|  | Develop And Implement mentorship and coaching plan and implement for Technical Department by December 2023 | Failure to undertake mentorship and coaching | Due to Unavailability of mentors and mentees; workloads | 1. Failure to have succession plans 2. Loss of institution memory | 1. Existing policy on mentorship and coaching 2. 2.Availability of Experienced professionals to mentor graduate Employees 3. Availability of trained mentors by PSC in the Technical Department | 1 | 4 | 4 | LOW | MAINTAIN |  | Human Resorce, office equipment (Furniture, desk, computers/laptops), telephone acces/airtime, stationery, Training Budget | 30th June 2024 | 1.number of mentorship engagements 2.Training reports, sensitization reports/attendance
|  | Train Management staff on Performance Management System by June 2023 |  | Inadequate budget due to austerity measures | 1. Lack of objectivity in staff perfromance appraisal. | 1. Sensitization on Performance Appraisal Procedure | 3 | 2 | 6 | MEDIUM | Monitor and control | Train the committee on Performance Management | Budget, Time |  | Training report,
|  | Provision of staff welfare facilities by 30th June 2023 | Failure to provide staff welfare facilities | Inadequate funding | Dissatisfied employee, staff turn-over, absenteeism | Annual Budget proposals | 4 | 1 | 4 | LOW | MAINTAIN |  | Human Resorce, office equipment (Furniture, desk, computers/laptops), telephone acces/airtime, stationery, Budget |  | Availability of staff welfare facilities
| Improve service delivery | Provision of security services for all TWWDA Premises | Failure to provide security for TWWDA premises | Incompetent Security Providers, Understaffed security personnel, Failure to adopt technology in security. Lack of or inadequate physical security for premises, Negligence of the security guard, | Loss of Agency assets, Damage of Agency Assets Damaged reputation | biometric system at the main door, Hand held metal detector, Additional of more guards, undersearch mirror, perimeter wall, additional of 5 CCTV cameras, loc able entrance and exit facilities, 24hr manning of premises | 1 | 5 | 5 | LOW | MAINTAIN |  | Budget, Personnel, Operation Procedures,Work instruction stationery, ICT equipment | 30th June 2024 | Security provided
|  | Facilitate management of 100% records by June 2023 | Failure to manage records due to misuse | Lack of proper storage and handling mechanism. Lack of integrity by the responsible officer. Unclear responsibility for management of records | Damage of reputation due to loss of stakeholder's confidence. | Locable cabinets, safes, record movement register, commitment to confidentiality of records during recruitment of staff, Existence of registry services | [6 empty] | Human Resource, office equipment (Furniture, desk, computers/laptops), telephone, stationery |  | Proper maintenance of records
|  | Provision of transport services for 100% tasks that require facilitation. | Failure to provide transport services | 1. Unvailability of vehicle due to breakdown/re-allocation/lack of service 2.Inadequate number of drivers/vehicles 3. Delayed payment of the service provider 4. Delayed/lack of timely requests by users 5.exhaustion of fuel | 1. Delayed transport services which delays service delivery. 2. Dissatisfied stakeholders | Safari request form, Maintenance schedules, hiring of taxi services,Timely invoicing by service providers, apportioning of fuel as per transport needs, Tracking of vehicles | 2 | 2 | 4 | LOW | MAINTAIN |  | Funds, Human resources, Stationery, Equipment |  | Transport facilitated
3 | SO 11 - Enhance Human Resource Capacity | maintain updated assest register and records | submission of inaccurate data/information late submission of reports | lack of committed workforce/support from staff members lack of/incomplete date/information in the reports to be submitted to the treasury | low rating from the treasury hence tainted reputation of the Agency loss of agency assets/damage of agency assets | 1. adherence to treasury guidelines and policies 2. standard operating procedure 3. clear assignment of roles and responsibilities 4.establishment of assets and management unit | 3 | 3 | 9 | MEDIUM | Monitor and control | follow up closely for submission of quarterly reports meet sets deadlines of every quarter. Frequent evaluation of reports before reporting | Human Resorce, office equipment (Furniture, desk, computers/laptops), telephone acces/airtime, stationery, funds for workshops | JUNE,2023 | quarterly reports
| S01 - To increase access to water supply services | To increase access to water supply services from 58% to 63% by FY2022/2023 by implementing the following: 1. Construction of Chogoria Water Supply Project 2. Construction of Kerugoya Kutus Water Supply Project 3. Construction of Murang'a South Water Supply Project 4. Construction of Murang'a Urban Water Supply Project 5. Construction of Gitije Kandugu Water Supply Project | Delay in project completion due to non-performance of Contractors | 1. Cashflow constraints faced by Contractors 2. Incompetent site staff 3. Inadequate materials, plant and equipment 4. Inclement weather | 1. Cost overruns 2. Dissatisfied stakeholders | 1. Selection of Contractor's based on past performance and conducting of due dilligence 2. Monthly site meetings held to review progress 3. Monitoring and evaluation of progress reports 4. Submission of programme of works by Contractor that is monitored for delay | 5 | 4 | 20 | High | MITIGATE | 1. Management meetings to be convened to resolve challenges and issues 2. Non-performing Contractors to be charged delay damages 3. Termination of Contracts for non-performing Contractors | Finances Human resource Transport | 30th June 2024 | Number of projects monitored. Number of timely done approvals. | CMTS
|  |  | Delay in project completion due to delayed approvals | 1. Agency delays to make timely applications 2. External institutions delay in granting timely approvals | 1.Cost overruns 2. Dissatisfied stakeholders | 1. Applications are made at Planning and Design phase of the project cycle 2. Internal escalation mechanism that includes follow up meetings, reminders through letters | 4 | 3 | 12 | Medium | Monitor and control | 1. Seeking assistance from Government Delivery Services and Ministry of Water, Sanitation and Irrigation Liaison officers |  |  | Number of applications Number of timely approvals
|  |  | Delay in project completion due to delayed disbursement of funds | 1. Inadequate budgetary allocation | 1.Cost overruns 2. Dissatisfied stakeholders | 1. Lobbying for timely allocation and disbursement of funding by the National Treasury and MoWSI 2. Stakeholder Forums (Politicians also invited to forums) | 4 | 4 | 16 | HIGH | MITIGATE | Maintainm, monitor and evaluate existing controls |  |  | Amount disbursed
|  |  | Failure to achieve targeted consumer connections due to lack of last mile connectivity component of projects | 1. Inadequate budgetary allocation | 1. Loss of revenue 2. Dissatisfied stakeholders 3. Lack of Return on Investment 4. Reduced Operational Efficiency | 1. Adequate Consumer Sensitization and Awareness 2. Lobbying for adequate funding | 3 | 3 | 9 | medium | MITIGATE | Implementation of policy directive from MoWSI on inclusion of last mile connectivity in all projects |  |  | Number of last mile connnectivity projects completed
|  |  | Completed construction not meeting technical specifications due to inadequate supervision | 1. Inadequate works supervision 2. Poor quality Planning and Design 3. Fraudulent and Collusion practices between the Contractor and works superintendent | 1. Increase in Maintenance Costs 2. Lack of Customer Satisfaction 3. Lack of Ownership by the End User | 1. Adherence toTechnical Specifications 2. Engagement of Competent Officers 3. Inspection and acceptance of works | 4 | 4 | 16 | High | Monitor and control | Standardisation of supervision procedures for GoK funded projects without consultants supervising works implementation |  |  | 1. Number of works taking over certificates issued
| S02 - To increase access to sanitation services | To increase access to sanitation services from 8% to 13% by FY2022/2023 by implementing the following: 1. Construction of Kerugoya Kutus Sewerage Project 2. Construction of Chogoria Sewerage Project 3. Construction of Chuka Sewerage Project | Delay in project completion due to non-performance of Contractors | 1. Cashflow constraints faced by Contractors 2. Incompetent site staff 3. Inadequate materials, plant and equipment 4. Inclement weather | 1. Cost overruns 2. Dissatisfied stakeholders | 1. Selection of Contractor's based on past performance and conducting of due dilligence 2. Monthly site meetings held to review progress 3. Monitoring and evaluation of progress reports 4. Submission of programme of works by Contractor that is monitored for delay | 5 | 4 | 20 | High | MITIGATE | 1. Management meetings to be convened to resolve challenges and issues 2. Non-performing Contractors to be charged delay damages 3. Termination of Contracts for non-performing Contractors |  |  | Number of projects monitored. Number of timely done approvals.
|  |  | Delay in project completion due to delayed approvals | 1. Agency delays to make timely applications 2. External institutions delay in granting timely approvals | 1.Cost overruns 2. Dissatisfied stakeholders | 1. Applications are made at Planning and Design phase of the project cycle 2. Internal escalation mechanism that includes follow up meetings, reminders through letters | 4 | 3 | 12 | Medium | Monitor and control | 1. Seeking assistance from Government Delivery Services and Ministry of Water, Sanitation and Irrigation Liaison officers |  |  | Number of applications Number of timely approvals
|  |  | Delay in project completion due to delayed disbursement of funds | 1. Inadequate budgetary allocation | 1.Cost overruns 2. Dissatisfied stakeholders | 1. Lobbying for timely allocation and disbursement of funding by the National Treasury and MoWSI 2. Stakeholder Forums (Politicians also invited to forums) | 4 | 4 | 16 | High | Monitor and control | Maintainm, monitor and evaluate existing controls |  |  | Amount disbursed
|  |  | Failure to achieve targeted consumer connections due to lack of last mile connectivity component of projects | 1. Inadequate budgetary allocation | 1. Loss of revenue 2. Dissatisfied stakeholders 3. Lack of Return on Investment 4. Reduced Operational Efficiency | 1. Adequate Consumer Sensitization and Awareness 2. Lobbying for adequate funding | 3 | 3 | 9 | Medium | Monitor and control | Implementation of policy directive from MoWSI on inclusion of last mile connectivity in all projects |  |  | Number of last mile connnectivity projects completed
|  |  | Completed construction not meeting technical specifications due to inadequate supervision | 1. Inadequate works supervision 2. Poor quality Planning and Design | 1. Increase in Maintenance Costs 2. Lack of Customer Satisfaction 3. Lack of Ownership by the End User | 1. Adherence toTechnical Specifications 2. Engagement of Competent Officers 3. Inspection and acceptance of works | 4 | 4 | 16 | High | MITIGATE | Standardisation of supervision procedures for GoK funded projects without consultants supervising works implementation |  |  | 1. Number of works taking over certificates issued
| S07 - Improve service delivery | Develop contract management policy/framework by FY2022/2023 | Failure to complete development of Contract management policy/framework | 1.Lack of adequate finances | 1. Cost overruns 2. Project delays 3. Legal and regulatory liability | 1. Strict adherance to Standard Operating Procedure for Contract Management 2. Adherance to Contract provisions (technical specifications, BoQs) | 3 | 4 | 12 | Medium | Monitor and control | Standardisation of supervision procedures for GoK funded projects without consultants supervising works implementation |  |  | 1. Number of works taking over certificates issued
1 | SO3 - Improve Brand Visibility | To undertake a customer satisfaction survey(CSSR) by 30th June 2024 | Failure toundertake a customer satisfaction survey(CSSR) by 30th June 2024 due to inadequate funding | 1.Delayed disbursment of funds 2. Reduced budgetary allocation | 1. Lower brand image 2. Delayed project implementation 3 Dissatisfied stakeholders | 1. Approved budget 2.Procedure For Monitoring Customer Satisfaction and Obtaining feedback Standard operating procedure 3. Timely budgetary allocation | 1 | 2 | 2 | LOW | Maintain existing controls and monitor | carry out a customer satisfaction survey. | 1. Finances 2.Human Resorce 3.Office equipment 4. ICT resources | 30th June 2024 | 1. Customer Satisfaction Surveys | HOD'S
|  | To implement the Communication strategy (includes branding and image strategy) within FY 2023/2024 | Failure to implement the communiction strategy due to Lack of funds | 1.inadequate funding from Treasury | 1. Low TWWDA visibility 2. Decreased brand awareness among stakeholders | 1. Existence of a Communication and PR function 2. Well mappped stakeholders 3.Approved budgets 4. Divisional work plans | 2 | 2 | 4 | LOW | Maintain existing controls and monitor | 1.Develop and implement a communication strategy. |  | 30th June 2024 | 1.Developed communication strategy. 2. Strategy implementation plan | MCC&PR
|  | To Undertake three (3) Corporate Social Responsibility initiatives by 30th June 2024 | Failure to Undertake three (3) Corporate Social Responsibility initiatives by 30th June 2024 due to Lack of funds | 1.Reduced budgetary allocation | 1. Poor Organizational image 2. Low stakeholder regard of TWWDA | 1. TWWDA CSR Policy 2.Approved annual budget. 3. Annual workplan 4. Quarterly progress reports | 1 | 3 | 3 | LOW | Maintain existing controls and monitor | undertake CSR activities. |  | 30th June 2024 | No. of CSR activities undertaken | MCC&PR
2 | SO5 - Enhance Partnerships and collaborations | Conduct one annual water and sanitation situation conference by 30th June 2024 | Failure to conduct one annual water and sanitation situation conference by 30th June 2024 due to lack of funds and competing activities within TWWDA. | 1. Competing projects within the Agency affecting the budget allocation 2. Heavy workload among TWWDA staff that affect the availability of the required team | 1.Project prioritization challenges for different regions | 1. Approved budget 2. Annual workplan 3. Quarterly progress reports | 4 | 2 | 8 | Medium | Existing control measures are ineffective | 1. Establish a planning committee 2. Early resource mobllization and involvement of partners. 3. Publicize the conference prior to the event dates |  | 30th June 2024 | Annual water and sanitation situation conference held | MCC&PR
| SO6 - Enhance Stakeholder Participation and Engagement | To implement the Community/stakeholder engagement strategy by 30th June 2024 | Lack of Community/stakeholder commitment | 1.Delayed disbursment of funds 2. Reduced budgetary allocation 3. Negative political interferance | 1. Slow project implementation 2. Negaive TWWDA brand | 1. Existence of a Communication and PR function 2.Well mapped of stakeholders. 3. Regular meetings with relevant communities, WSPs and County Governments | 1 | 4 | 4 | Low | Maintain existing controls and monitor | Engage community/ stakeholders in fora |  | 30th June 2024 | No. of Community/stakeholder engagements | MCC&PR
|  | Undertake climate change, adaptation and mitigation programmes by planting minimum 30,000 trees in the FY 2023/2024 | Failure to plant 30,000 trees within the FY 2023/2024 due to unfavourable weather conditions | 1. Unpredictable weather patterns | 1.Deteriorating natural resources in our area of jurisdiction 2.Reduced stakeholder engagement | 1. Approved annual budget 2. Regualr stakeholder engagement, 3.Support of TWWDA Board and Management, | 1 | 3 | 3 | LOW | Maintain existing controls and monitor | Grow 30,000 trees |  | 30th June 2024 | Minimum 30,000 trees planted | MCC&PR
| SO3 - Improve Brand Visibility |  | Negative TWWDA brand due to bad publicity | 1. Natural disasters/calamities 2. Political interferance | 1. Poor Organizational image 2. Damaged Agecny reputation 3. Low stakeholder confidence. | 1. Communication Policy 2. Stakeholder engagement strategy 2.Response to media SOP | 4 | 2 | 8 | Medium | Maintain existing controls and monitor (Existing controls are effective but | 1. Regular meetings with various stakeholders 2. Positive media engagement |  | 30th June 2024 | No. of positive TWWDA features in the press | MCC&PR
1 | SO7- Improve Service Delivery | 1. To procure 100% based on the approved Procurement Plan by the end of June 2023. | Failure to comply with the Plan due to non-responsiveness/or lack of capacity of External Providers | 1. Inadequate Evaluation and due diligence. | 1. Loss of revenues as a result of time-value of money in the light of time passage 2. Delayed orders/Lengthy Lead-times and Delivery times 3. Dissatisfied stakeholders e.g Users 4. Reduced operational efficiency | 1. Timely drawing of procurement plans based on budgetary estimates 2. Formal communication with the external provider 3. Competitive selection of external providers who can offer lengthy credit facilities 4. Appointment of competent tenders` preparation and evaluation teams 5. Compliance with the PPRA guidelines | 3 | 3 | 9 | MEDIUM | Monitor and control | 1. LPOs/LSOs Financing, 2. Enhanced implementation of the existing controls | Human Resource, office equipment (Furniture, desk, computers/laptops), telephone acces/airtime, motorvehicle, stationery | 30th June 2024 | 1. Number of late deliveries made as at the end of 30th June 2024 | MSCM
2 | SO7- Improve Service Delivery | To dispose of all (100%) the identified low-value disposable items by the end of FY 2022-2023 | Failure to dispose due to Non-responsiveness of buyers | 1. Poor condition of the disposable items 2. Inflated prices of the disposables | 1. Accumulation of Obsolete items 2. Storage costs and losses 3. Increased Stores Work-load | 1. Wide circulation of the Disposal adverts 2. Market driven costing of disposables. | 3 | 1 | 3 | Low | maintain the controls | Maintain the existing measures | Human Resource, office equipment (Furniture, desk, computers/laptops), telephone acces/airtime, motorvehicle, stationery | 30th June 2024 | Percentage of the low-valued items diposed against the total number of the identified listed disposables.
1 | SO4- Improve Financial Sustainability | To mobilize KES 300 Million for the development of National Public Water and Sanitation Works in the Financial Year 2023/2024. | Failureto mobilize KES 300 Million for the development of National Public Water and Sanitation due to reduced support by development partners | 1. Project Concept Notes(PCN) and Project financing proposals for funding that don't meet the development partners' requirements 2. failure to adhere to requirements of the existing/previous development partners' funding policy and guidelines 3. Delays in Resource Mobilization activities due to pandemic-related Issues 4. Changes in government policies/guidelines that freeze the implementation of new projects 5. Government restrictions and ceiling on borrowing 7. Delay in PCN approvals 8. Inability to market the Concept Paper and Project proposal for funding. | 1. Inadequate funding to implement activities from the strategic plan 2. Delayed projects 3. Dissatisfied stakeholders 4 Reduced operational efficiency . | 1. Monitor compliance with signed Financing Agreements and MOUs 2 Monitoring adherence to requirements of the development partners' funding policy and guidelines 3. Incorporating New project concept paper and project financing proposal to the Parent Ministry for future funding consideration in the Medium Term Expenditure Framework (MTEF) 4. Attending training on the Development of quality concept papers conducted by the parent ministry in collaboration with the National Treasury 5. Lobbying with TNT,Parent Ministry and development partners | 3 | 4 | 12 | Medium | Mitigate | 1. Develop New project PCN, Feasibility and submit for approval. 3. Building Capacity for staff on advocacy and networking 4. Enhance Lobbying with TNT, Parent Ministry, and development partners 5. Appointment of Project Committee to review the PCN before submission for approval by the MoWSI and TNT | 1. Time 2. Finances 3. Human Resource | 30th June 2024 | 1. Amount of funds mobilized through RM strategy activities 2. No. of the new project, PCN developed and submitted for approval 3. No. of staff trained in advocacy and networking 4. No. of PCN reviewed by the project committee | CMF & RM
2 | SO5- Enhance partnership and Collaboration | To establish 2 N0. partnerships and collaborations in the Financial Year 2023/2024 | Failure to establish 2 N0. partnerships and collaborations due to lack of supportive legislation | 1. Lack of political goodwill 2. Poor institution reputation | 1. Inadequate funding 2. lack of new programmes 3.Dissatisfied stakeholders | 1. Holding meetings with potential partners 2. Compliance with laws and regulations | 3 | 3 | 9 | Medium | Mitigate | 1. Research on the interest of existing and New development partners in the Water sector through visiting their embassy or Desktop research. 2. Engage the private sector in water infrastructure development through PPP after legistlation. Lobbying with Parliamentary Accounts Commiittee, Ministry of Water, Sanitation and Irrigation | 1. Time 2. Finances 3. Human Resource | 30th June 2024 | 1. No. of Partnership and Collaboration established 2. No. of projects initiated through PPPs | CMF & RM
1 | SO6-Enhance Stakeholder Participation and Engagement | To develop a land and wayleave acquisition plan/strategy by the end of FY 2022/23 | Failure to develop a land and wayleave acquisition plan/strategy due to time constraints | 1. departmental workload | 1. Delayed projects 2. unavailable land for project implementation 3. unidentified parcels of land owned by the Agency 4. Inadequate information on land related liabilities | 1. Existance of a Land Acquisition and Compensation Committee 2. Existing Land and Wayleaves SOP 3. Budget allocations | 3 | 3 | 9 | MEDIUM | MITIGATE | 1. Reconstitute the Land Acquisiton and Compensation Committee 2. Train the Committee on development of the Policy 3. Benchmark with other Institutions 4. Review the existing SOPs | Human Resource, office equipment (Furniture, desk, computers/laptops), telephone acces/airtime, motorvehicle, stationery | 30th June 2024 | An approved Policy | CS & MLS
2 | SO7- Improve Service Delivery | To reduce the number of land and wayleaves related complaints from 60% to 85% by end of FY 2022/2023 | 1.Failure to resolve the complaints due to Litigation | 1.Lack of a proper land and wayleave acquisition plan/strategy 2. Non compliance with the Land Laws 3. Lack of stakeholder engagement prior to land acquistion | 1.Increased Court cases 2. Delayed projects 3. Dissatisfied Land owners | 1.Existence of a Grievance redress Committee to solve disputes 2. Alternative Dispute Resolutions | 3 | 3 | 9 | MEDIUM | MITIGATE | 1. Train the Legal Staff on Land Law processes 2. Sensitize the Project officers on complaints handling
|  | To circulate Board papers from 5 Days prior to 7 days prior to scheduled Meeting | Late submission of Board Papers due to late submission of reports by Heads of departments/divisions | Departmental Workload Negligence | 1. Dissatisfied Board Members 2. Wrong Board decisions | 1. Circulation of the Board Almanac to all Departments/Divisions 2. Notification to Heads of Departments/Divisions for timely submission of Board papers | 3 | 2 | 6 | MEDIUM | MITIGATE | 1. Sensitize the Staff and Management on the need to submit Board papers on time

## Sheet1
[7 empty] | INHERENT RISK ASSESMENT | [5 empty] | RISK TREATMENT PLAN |  |  |  |  | RESIDUAL RISK ASSESSMENT |  |  |  |  | RISK TREATMENT PLAN
Risk ID | SRATEGIC OBJECTIVE | DEPARTMENTAL OBJECTIVE | RISK | CAUSE / SOURCE | CONSEQUENCE DESCRIPTION | EXISTING CONTROLS | LIKELIHOOD | IMPACT | RISK SCORE | RISK LEVEL | RISK TREATMENT | ACTIVITIES TO BE DONE | RESOURCES | TIMELINES | STATUS/KPI | RESPONSIBILITY | OBJECTIVE EVIDENCE | LIKELIHOOD | IMPACT | RISK SCORE | RISK LEVEL | EVALUATION IN EFFECTIVENESS | ACTIVITIES TO BE DONE (2023/2024) | RESOURCES | TIMELINES | STATUS/KPI | RESPONSIBILITY | OBJECTIVE EVIDENCE
1 | SO6-Enhance Stakeholder Participation and Engagement | To develop a land and wayleave acquisition plan/strategy by the end of FY 2022/23 | Failure to develop a land and wayleave acquisition plan/strategy due to time constraints | 1. departmental workload | 1. Delayed projects 2. unavailable land for project implementation 3. unidentified parcels of land owned by the Agency 4. Inadequate information on land related liabilities | 1. Existance of a Land Acquisition and Compensation Committee 2. Existing Land and Wayleaves SOP 3. Budget allocations | 2 | 3 | 6 | MEDIUM | Mitigate | 1. Reconstitute the Land Acquisiton and Compensation Committee 2. Train the Committee on development of the Policy 3. Benchmark with other Institutions 4. Review the existing SOPs | Human Resource, office equipment (Furniture, desk, computers/laptops), telephone acces/airtime, motorvehicle, stationery | 30th June 2023 | An approved Policy | CS & MLS | Draft policy prepared | 3 | 3 | 9 | MEDIUM | Control measures were not effective | 1. Reconstitute the Land Acquisiton and Compensation Committee 2. Train the Committee on development of the Policy 3. Benchmark with other Institutions 4. Review the existing SOPs | Human Resource, office equipment (Furniture, desk, computers/laptops), telephone acces/airtime, motorvehicle, stationery | 30th June 2024 | An approved Policy | CS & MLS | Draft policy prepared
2 | SO7- Improve Service Delivery | To reduce the number of land and wayleaves related complaints from 60% to 85% by end of FY 2022/2023 | 1.Failure to resolve the complaints due to Litigation | 1.Lack of a proper land and wayleave acquisition plan/strategy 2. Non compliance with the Land Laws 3. Lack of stakeholder engagement prior to land acquistion | 1.Increased Court cases 2. Delayed projects 3. Dissatisfied Land owners | 1.Existence of a Grievance redress Committee to solve disputes 2. Alternative Dispute Resolutions | 3 | 3 | 9 | HIGH | Mitigate | 1. Trian the Legal Staff on Land Law processes 2. Sensitize the Project officers on complaints handling | Human Resource, office equipment (Furniture, desk, computers/laptops), telephone acces/airtime, motorvehicle, stationery | 30th June 2023 | 1. Level of Reduction of Court cases by end FY 2022/2023 2. No of Titles transferred by end of FY 2022/2023 3. No. of complaints received versus number of complaints solved | CS & MLS | Court records, minutes of stakeholder meetings | 3 | 3 | 9 | MEDIUM | Control measures were not effective | 1. Train the Legal Staff on Land Law processes 2. Sensitize the Project officers on complaints handling | Human Resource, office equipment (Furniture, desk, computers/laptops), telephone acces/airtime, motorvehicle, stationery | 30th June 2024 | 1. Level of Reduction of Court cases by end FY 2022/2023 2. No of Titles transferred by end of FY 2022/2023 3. No. of complaints received versus number of complaints solved | CS & MLS | Court records, minutes of stakeholder meetings
|  | To circulate Board papers from 5 Days prior to 7 days prior to scheduled Meeting | Late submission of Board Papers due to late submission of reports by Heads of departments/divisions | Departmental Workload Negligence | 1. Dissatisfied Board Members 2. Wrong Board decisions | 1. Circulation of the Board Almanac to all Departments/Divisions 2. Notification to Heads of Departments/Divisions for timely submission of Board papers | 3 | 2 | 6 | MEDIUM | Mitigate | 1. Sensitize the Staff and Management on the need to submit Board papers on time | Human Resource, office equipment (Furniture, desk, computers/laptops), telephone acces/airtime, motorvehicle, stationery | 30th June 2023 | 1. Number of Days within which Board papers were circulated | CS & MLS | dates of circulation of agendas and documents | 3 | 2 | 6 | MEDIUM | Control measures were not effective | 1. Sensitize the Staff and Management on the need to submit Board papers on time | Human Resource, office equipment (Furniture, desk, computers/laptops), telephone acces/airtime, motorvehicle, stationery | 30th June 2024 | 1. Number of Days within which Board papers were circulated | CS & MLS | dates of circulation of agendas and documents