## BQ Detail
ITEM | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
BILL 1 | PRELIMINARY & GENERAL ITEMS
Contractual Requirements
1A110 | Provide Performance Bond | sum | 1
1A120 | Insurance of Works | sum | 1
1A130 | Third Party Insurance | sum | 1
Specified Requirements
1A211.1 | Establishment and removal of offices for Engineer's staff | sum | 1
1A211.2 | Maintenance of offices for Engineer's staff | sum | 1
Services for the Engineer's Staff
1A221.2 | Maintain, insure, fuel, lubricate, and servicing of the transport vehicle in use by the Engineer during the contract period - Allow approximately 5,000 km per vehicle month | Veh-Months | 6
Provide Equipment for use by Engineer's Staff
1A222 | Provide Engineer's staff mobile phone Airtime for the duration of the Contract. | months | 6
1A231 | Provision of to the Employer and Engineer's offices Equipment including computers, photocopier | Item | 1
1A260 | Allow a proviosnal sum for Material testing of Concrete works during construction | PS | 1 | 100000 | 100000
Temporary Works
1A273 | Provide and establish project publicity sign boards (location as directed on site) | No. | 2
1A275 | Allow for River Diversion, incuding construction of cofferdam | Item | 1
Plant
1A333 | Mobilization and demobilization of contractors plant and equipment | sum
Provisional Sum
1A421 | Allow a Provisonal sum of KSh500,000 for the attendance for the Engineers' support staff as directed by the Engineer. | PC-Sum | 1 | 500000 | 500000
1A422 | Allow a Provisional Sum of Ksh 100,000 for Desilting within the Reservoir | Item | 1 | 100000 | 100000
1A423 | Allow a Provision Sum of Ksh 100,000 for Demolition of existing Masonry embankment and disposal of waste material; as directed by the Engineer | Item | 1 | 100000 | 100000
Total Collection carried to Summary Page
ITEM | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
BILL 2 | EMBANKMENT AND ANCILLARY STRUCTURES
Site Clearance
2D110.1 | General clearence of of reservoir area and embankment area | m² | 3000
2D110.2 | Clearance of site for the structures (embankment, diversion) | m² | 250
CONCRETE WORKS AND REINFORCEMENT
Provision of Concrete
2F611 | Provision of blinding concrete designed mix Grade 15, 20mm aggregate, cement to BS 12 or otherwise specified for the Embankment | m2 | 200
Reinforced
2F621 | 150mm Grade 25 Reinforced Concrete Slab to valve chamber floor slab and roof slab | m³ | 0.675
2F744 | 500mm wide concrete Grade 25 for 5m high Embankment Stem & Wing wall | m³ | 260
2F722 | 200mm thick Upstream and Downstream Apron | m³ | 30
CONCRETE ANCILLARIES
Formwork fair finish.
2G215 | Embankment Wall | m2 | 378
Reinforcement.
2G524 | Deformed high yield steel bars to BS 4449 diameter 12mm | kg | 3303.36
2G523 | Deformed high yield steel bars to BS 4449 diameter 10mm | kg | 2020.48
Concrete Accessories.
2G811 | Finishing of top surfaces, wood float finish to all masonry walls; valve chamber | m² | 2
2G812 | Finishing of top surfaces, steel trowel finish to all masonry walls; valve chamber | m² | 2
Inserts.
2G832 | Provide and install 63mm uPVC Class C Drain pipe from valve chamber sump | m | 1
| Total Collection Carried to Summary Page |  |  |  | 0
ITEM | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
BILL 3 | DRAW OFF & INTAKE TOWER
Rates to include disposal or stockpiling for re-use as directed by the Engineers
3E412 | Excavate in normal materials for the Offtake tower Foundation. The rate shall allow keeping the sides free from collpase | m3 | 6.25
3E421 | Ditto in weathered materials | m3 | 1.875
3E431 | Ditto in Rock material | m3 | 1.25
CLASS F: IN SITU CONCRETE
Provision and Placing of concrete including finishing of top and formed surfaces to the approval of the Engineer.
3F122 | Strength Grade 15/20 (1:3:6) blinding concrete with sulphate resisting cement | m3 | 0.46875
3F222 | Strength Grade 25/20 (1:1.5:3) reinforced concrete to offtake tower Foundation base , with sulphate resisting cement | m3 | 2.5
Reinforcement
Deformed high yield steel bars to BS 4449
3F524 | Nominal Diameter 12 mm | Kg | 50
Class I: Pipework
All steel pipes and fittings shall be epoxy coated, PN16. Supply, handle, install and test the following steel pipes and fittings.
3I311.1 | 75mm dia GI Draw off pipe | No. | 3
3I311.2 | 100mm dia GI Scour pipe | No | 3
3I711.3 | 75mm dia perforated GI Draw off pipe | No. | 1
Class J:Pipework Fittings & Valves
3J311 | 90˚ 75mm GI Bend | No | 1
3J811.1 | 75mm Double Flanged sluice Valve | No | 1
3J811.2 | 100mm Double Flanged sluive valve | No | 1
Class K: Pipework-Manholes and Pipework Ancillaries
3K131 | Valve chamber for Draw off pipe | No | 1
3K132 | Valve chamber for Scour Pipe | No | 1
Total Collection Carried to Summary Page
Bill 4 | Ancillary Works
Class X:Miscellaneous works
4X20 | Provide and place rubble stone erosion barriers as directed | m2 | 120
| Allow a Provisional Sum for Construction of Communal water point and necessary pipe work from the draw-off Valve Chamber | Item | 1
Total carried to Summary Page

## Summary sheet
Grand Summary
Bill Item | Description | Amount
1 | PRELIMINARY & GENERAL ITEMS
2 | EMBANKMENT AND ANCILLARY STRUCTURES
3 | DRAW OFF & INTAKE TOWER | 0
4 | MISCELLANEOUS | 0
5 | SUB-TOTAL 1
6 | ADD 5% CONTINGENCY
GRAND TOTAL